## Number of KPIs and Targets
SUMMARY OF KPI's and TARGETS PER DEPARTMENT
| OMM | Technical Services | Community Services | Finance | Corporate | Total KPIs
Municipal Institutional Development and Transformation | 2 | 0 | 4 | 3 | 17 | 26
Basic Service Delivery | 3 | 17 | 7 | 0 | 0 | 27
Local Economic Development | 1 | 0 | 30 | 1 | 0 | 32
Financial Viability and Management | 3 | 3 | 1 | 21 | 4 | 32
Good Governance | 24 | 3 | 3 | 4 | 7 | 41
Cross Cutting | 3 | 3 | 3 | 3 | 2 | 14
| 36 | 26 | 48 | 32 | 30 | 172

## DRAFT APR 2022 2023
ORGANISATIONAL SCORECARD FOR 2022/2023
OFFICE OF THE MUNICIPAL MANAGER
ANNUAL PERFORMANCE REPORT 2022/2023
INDICATORS |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | BACKLOG | ANNUAL TARGET 2022/2023 |  | ACHIEVED/NOT ACHIEVED | REASONS FOR NON-ACHIEVEMENT | MEASURES FOR IMPROVEMENT | BUDGET | WARD INFORMATION | MEANS OF VERIFICATION (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | B2B REF N0. |  |  |  |  | 2021/2022 |  | TARGET | ACTUAL
KEY PERFORMANCE AREA: BASIC SERVICE DELIVERY | OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES | OUTCOME 6: AN EFFICIENT, COMPETITIVE AND RESPONSIVE ECONOMIC INFRASTRUCTURE NETWORK | BSD 1 | B2B-5 | To ensure the provision, upgrade and construction of infrastructure and services that enhance socio economic development within the municipality | Monitor the Spending of Municipal Infrastructure Grant Expenditure to achieve 100% | Percentage of Municipal Infrastructure Grant spent | New | New | New | 100% | 100% | Achieved | N/A | N/A | R17,781m | 1,2,3,4,5,6 & 7 | Progress Report showing the % progress on site and expenditure to date, invoices and Expenditure Report for MIG Projects | Municipal Manager
[6 empty] | Monitor the Spending of Small Town Rehabilitation Grant Expenditure to achieve 100% | Percentage of Small Town Rehabilitation Grant spent | New | New | New | 100% | 100% | Achieved | N/A | N/A | R14m | 3 | Progress Report showing the % progress on site and expenditure to date, invoices and expenditure Report for Small Town Rehabilitation | Municipal Manager
[6 empty] | Monitor the Spending of Integrated National Electrification Programme to achieve 100% | Percentage of budget of the integrated National Electrification Programme spent | New | New | New | 100% | 100% | Achieved | N/A | N/A | R15m | 1,2,3,4,5,6 & 7 | Progress Report showing the % progress on site and expenditure to date, invoices and expenditure Report for integrated National Electrification Programme | Municipal Manager
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT1 | B2B-5 | To ensure a functional organisational structure | Review of the municipal organogram | Date of adopted reviewed organogram | 2022-06-30 | 2022-06-29 | N/A | 2023-06-30 | 2023-05-31 | Achieved | The preparation of the IDP approval was completed before time hence the item was tabled to Council early that anticipated. | N/A | N/A | Institutional | Copy of Organisational structure and Council resolution | Municipal Manager
|  |  | MIDT13 | B2B_5 | To ensure skills development and training to improve access to economic growth opportunities for marginalized groups within the municipality | Public Employment Programmes job opportunities created | Number of work opportunities created through EPWP (static after Q1 recruitment. This must be 300 at all times) | New | New | New | 300 | 341 | Achieved | N/A | N/A | R5,7m | Ward 1,2,3,4,5,6,7 | EPWP Projects List of beneficiaries | Municipal Manager
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT | OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME | OUTCOME 4: DECENT EMPLOYMENT THROUGH INCLUSIVE GROWTH | LED9 | B2B-1 | To Promote emerging Businesses | Monitor the number of Award made to BBBEE level 1 companies for bids more than R30 000. | No. of bids above R30 000 awarded to BBBEE level 1 companies | New | New | New | 30 | 26 | Not Achieved | The municipality has eamarked on the cost cutting measures hence they were only 8 transactions for in Quarter 1. | Target will be reviewed in the new FY 2023/2024, by Q1, 30/09/2023 | N/A | Ward 1,2,3,4,5,6,7 | Schedule of awards and copy of purchase order | Municipal Manager
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN9 | B2B_4 | To ensure effective and efficient supply chain management system | Appointment of Bid Committees (BSC, BEC and BAC) in line with Municipal SCM Policy and regulations. | Date of appointment of all Bid Committees | 2021-07-31 | 2021-07-31 | N/A | 2022-07-31 | BSC-01 July 2022, BEC-06 July 2022, 07 July 2022 and BAC-08 July 2022 | Achieved | N/A | N/A | N/A | Institutional | Schedule of Bid Committee members and copy of appointment letters signed by the Municipal Manager with acceptance by members | Municipal Manager
[6 empty] | Appointment of Service providers within 14 working days after the BAC meetings | Number/Cycle of days of Appointments made after the BAC processes | New | New | New | 14 days | Not Achieved | Not Achieved | Due to the unavailability of some committee members, the meeting did not quorade hence the number of days was not achieved. | A BAC meeting plan will be discussed with the members including adhering to the schedule of meetings and forwarded to all members, by 30/09/2023, Q1 of the 2023/2024 financial year, to be able to achieve the 14 days BAC Cycle | N/A | Institutional | Appointment letters and copy of Attendance registers for BAC | Municipal Manager
|  |  | FIN3 | B2B_4 | To ensure compilation of a credible Annual Financial Statements | Compilation and submission of the AFS to Auditor General | Date the AFS is submitted to Auditor General | 2021-08-31 | 2021-08-31 | N/A | 2022-08-31 | 2022-08-31 | Achieved | N/A | N/A | N/A | Institutional | AFS and proof of receipt from the Office of the Auditor General | Municipal Manager
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1 | B2B_3 | To implement and maintain effective enterprise risk management system | Finalise Risk Management Workshop | No of risk management Workshops Conducted | 2 | 2 | N/A | 2 | 2 | Achieved | N/A | N/A | N/A | Institutional | Risk register and workshop registers | Municipal Manager
[6 empty] | Submission of Risk Management Policy and Strategy | Date of Risk Policy/Strategy submitted to council | 2022-06-30 | 2022-06-30 | N/A | 2023-06-30 | 2023-06-29 | Achieved | N/A | N/A | N/A | Institutional | Reviewed risk management strategy & Policy and Council resolution | Municipal Manager
[6 empty] | Functional Risk Management through risk committee meetings | Number of risk management meetings held | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Risk management committee minutes and attendance register | Municipal Manager
|  |  | GG8 | B2B_3 | To provide reasonable assurance on the adequacy and effectiveness of internal control system | Review and approve the internal audit plan | Date Internal Audit Plan approved by Audit Committee | 2022-06-30 | 2022-06-28 | N/A | 2023-06-30 | 2023-06-29 | Achieved | N/A | N/A | N/A | Institutional | Audit Plan and Audit committee minutes | Municipal Manager
[6 empty] | Implementation of the Internal Audit Plan | Number of Internal Audit Progress Reports produced and submitted to MANCO and Audit Committee | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports, Audit committee and MANCO minutes and registers | Municipal Manager
[6 empty] | Review and submit Internal audit charter to the audit committee for approval | Date of approval of the Internal Audit Charter by Audit Committee | 2022-06-30 | 2022-06-28 | N/A | 2023-06-30 | 2023-06-29 | Achieved | N/A | N/A | N/A | Institutional | Copy of the Internal Audit charter and audit committee minutes and register | Municipal Manager
[6 empty] | Review and submit the Performance and Audit Committee charter | Date of approval and adoption of the Performance and Audit Committee charter by Council | 2022-06-30 | 2022-06-30 | N/A | 2023-06-30 | 2023-06-29 | Achieved | N/A | N/A | N/A | Institutional | Council resolution and copy of audit charter | Municipal Manager
|  |  | GG4 | B2B_3 | To transform the Municipality into performance driven Municipality ensure an effective Audit and Performance Committee | Coordinate and hold the Audit Committee Meetings | Number of Audit Committee Meetings Held | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Minutes and attendance registers | Municipal Manager
|  |  |  | B2B_3 |  | Coordinate and hold performance Audit Committee Meetings | Number Performance Audit Committee Meetings Held | 2 | 2 | N/A | 2 | 4 | Achieved | N/A | N/A | N/A | Institutional | Minutes and attendance registers | Municipal Manager
|  |  | GG10 | B2B_3 | To transform the municipality into a performance driven institution | Performance Reports on achieved and not achieved targets submitted to Council | Number of Performance Reports Submitted to Council | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | PMS Report and Council resolution | Municipal Manager
|  |  |  | B2B-5 |  | Signing of annual performance agreements for Senior Managers | Number of Performance Agreements Signed | 5 | 5 | N/A | 5 | 5 | Achieved | N/A | N/A | N/A | Institutional | Copy of signed agreements for senior managers | Municipal Manager
|  |  |  | B2B_3 |  | Conduct performance appraisals for section 56/57 | Number of Section 56/57 employees appraisals conducted | 1 | 1 | N/A | 1 | 0 | Not achieved | Performance appraisals were scheduled to take place on the 30/06/2023, but due to the availability of the panel members (SALGA Provincial Assembly) the assessments was postponed. | Section 56/57 employees appraisals will be conducted by Q1, 30/09/2023 of the 2023/2024 FY | N/A | Institutional | Performance appraisal reports | Municipal Manager
|  |  |  | B2B_4 |  | Conduct performance appraisals for departmental staff | Number of Office of the MM employees appraisals conducted | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Performance appraisal minutes and register | Municipal Manager
|  |  |  | B2B_3 |  | To ensure that the mid-year Performance Report is prepared and submitted | Date of Mid Year Performance report submitted to Mayor, COGTA, Provincial and National Treasury | 2022-01-25 | 2022-01-25 | N/A | 2023-01-25 | 2023-01-25 | Achieved | N/A | N/A | N/A | Institutional | Mid Year performance report and proof of submission | Municipal Manager
|  |  |  | B2B_3 |  | To ensure that the mid -year Budget Report is prepared and submitted | Date of Mid Year Budget Report submitted to Mayor, COGTA, Provincial and National Treasury | 2022-01-25 | 2022-01-25 | N/A | 2023-01-25 | 2023-01-25 | Achieved | N/A | N/A | N/A | Institutional | Report and proof of submission | Municipal Manager
|  |  |  | B2B_3 |  | To prepare and table the draft Annual report to Council | Date Draft Annual Report tabled to Council | 2022-01-31 | 2022-01-31 | N/A | 2023-01-31 | 2023-01-25 | Achieved | N/A | N/A | N/A | Institutional | Draft AR and Council Resolution | Municipal Manager
|  |  |  | B2B_3 |  | Coordinate the Oversight committee meeting to consider the adoption of the annual report | Date of Oversight Committee (MPAC) Meeting | 2022-03-31 | 2022-03-15 | N/A | 2023-03-31 | 2023-03-15 | Achieved | N/A | N/A | N/A | Institutional | Oversight report and Minutes | Municipal Manager
|  |  |  | B2B_3 |  | Oversight Process Facilitated and Adopted | Date of Oversight report adoption by council | 2022-03-31 | 2022-03-31 | N/A | 2023-03-31 | 2023-03-30 | Achieved | N/A | N/A | N/A | Institutional | Council resolution | Municipal Manager
|  |  |  | B2B_3 |  | To finalise and adopt Annual Report | Date of Annual Report adoption by Council | 2022-03-31 | 2022-03-31 | N/A | 2023-03-31 | 2023-03-30 | Achieved | N/A | N/A | N/A | Institutional | Council resolution | Municipal Manager
|  |  | GG5 | B2B_3 | Ensure Functional Public Municipal Accounts Committee | Coordinate Municipal Public Accounts Committee meetings | Number of quarterly Municipal Public Accounts Committee Meetings Held | 4 | 2 | 2 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Minutes and registers | Municipal Manager
|  |  | GG6 | B2B_3 | To ensure continuous engagement with ward constituencies | Coordinate the Ward Committee meetings in 7 wards | Number of ward committee meetings held | 84 | 33 | 51 | 84 | 81 | Not Achieved | The meeting was scheduled to sit but some ward committee members were unable to attend the meeting due to the engagements hence there was no quorum in Q1 | A schedule of meetings will be circulated to all ward committee members by Q1, 30/09/2023 in the 2023/2024 Financial Year. | N/A | Ward1,2,3,4,5,6,7 | Minutes and attendance Registers | Municipal Manager
|  |  | GG6 | BSB _3 |  | Coordinate the Public Meetings held | Number of Public Meetings held | 28 | 27 | 1 | 28 | 49 | Achieved | N/A | N/A | N/A | Ward 1-7 | Minutes & Attendance Registers | Municipal Manager
|  |  | GG8 | B2B_3 | To provide reasonable assurance on the adequacy and effectiveness of Internal Control system. | Review of the Communication Strategy | Date of adopting the reviewed Communication Strategy | 2022-06-30 | 2022-06-30 | N/A | 2023-06-30 | 2023-06-29 | Achieved | N/A | N/A | N/A | Institutional | Council Resolution and copy of Communication Strategy | Municipal Manager
|  |  | GG9 | B2B_3 | To ensure that services provided to the municipality by the service providers is of high quality | Assess and Report on Service Providers Performance | Number of Reports on the assessment of service providers | 2 | 2 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on Service provider performance | Municipal Manager
KEY PERFORMANCE AREA : CROSS CURRING ISSUES
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC1 | B2B_2 | To ensure strategic development and management of the municipality’s Integrated Development Plan | Development and approval of the IDP/ Budget Process Plan | Date of adoption of the 2023/2024 IDP/ Budget Process Plan | 2021-08-31 | 2021-08-26 | N/A | 2022-08-31 | 2022-08-31 | Achieved | N/A | N/A | N/A | Institutional | IDP Process plan and Council Resolution | Municipal Manager
|  |  |  | B2B_2 |  | Coordinate the IDP Representative Forum meetings | Number of IDP Representative Forum meetings | 2 | 2 | N/A | 2 | 2 | Achieved | N/A | N/A | N/A | Institutional | Attendance registers and/or minutes | Municipal Manager
|  |  |  | B2B_2 |  | Adoption and Implementation of the Integrated Development Plan (IDP) focusing on delivery of 10 critical municipal services | Date of adoption of the 2023/2024 IDP | 2022-06-30 | 2022-06-30 | N/A | 30 June 2023 (Final adoption) | 2023-05-31 | Achieved | N/A | N/A | N/A | Institutional | Q3 Draft IDP and Council Resolution, Q4 Final IDP and Council Resolution | Municipal Manager
MKHAMBATHINI MUNICIPALITY
CORPORATE SERVICES
ANNUAL PERFORMANCE REPORT 2022/2023
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | BACKLOG | ANNUAL TARGET 2022/2023 |  | ACHIEVED/NOT ACHIEVED | REASONS FOR NON-ACHIEVEMENT | MEASURES FOR IMPROVEMENT | BUDGET | WARD INFORMATION | MEANS OF VERIFICATION (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | B2B REF N0. |  |  |  |  | 2021/2022 |  | TARGET | ACTUAL
NKPA: MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT1 | B2B-5 | A functional organizational structure | Report on the vacancies filled as per the staff regulations | Number of reports on vacancies filled | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on filling of vacancies | Corporate Services
|  |  | MIDT2 | B2B-5 | To ensure sound human resource management | Monthly Leave reconciliation | Number of leave reconciliation report | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Monthly Leave reconciliation reports | Corporate Services
[6 empty] | Training/workshop of employees on the reviewed and new Corporate policies | Number of workshop/ trainings held on corporate policies | New | New | New | 1 | 1 | Achieved | N/A | N/A | N/A | Institutional | Attendance registers and workshop/training reports | Corporate Services
[6 empty] | Cascading of IPMS to all employees | Number of reports on implementation of IPMS | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on implementation of IPMS | Corporate Services
[6 empty] | Reporting on staff attendance being monitored | Number of monthly reports on staff attendance | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Monthly reports on staff attendance' | Corporate Services
|  |  | MIDT3 | B2B-5 | To ensure effective and efficient Library Services | Reporting on Library outreach programmes implemented | Number of reports on outreach programmes | 2 | 2 | N/A | 2 (Q1 Holiday Programme, Q2 Library Week) | 2 (Q1 Holiday Programme, Q2 Library Week) | Achieved | N/A | N/A | 80000 | Institutional | Reports on outreach programmes and pictures | Corporate Services
|  |  | MIDT4 | B2B-5 | To ensure that municipal staff is skilled according to job requirements | Reporting on the Implementation of WSP | Number of training reports on WSP implementation | 4 | 4 | N/A | 1 | 1 | Achieved | N/A | N/A | 680000 | Institutional | Reports on WSP implementation | Corporate Services
[6 empty] | Date by which the WSP and the ATR is submitted to LGSETA | Submission of the WSP and ATR to LGSETA by 30 April 2023 | 2022-04-30 | 2022-04-26 | N/A | 30-Apr-2023 | 28-Apr-2023 | Achieved | N/A | N/A | N/A | Institutional | Acknowledgement of receipt from LGSETA and proof of submission | Corporate Services
|  |  | MIDT5 | B2B-5 | To promote occupational health and safety in the workplace | Functional Health and Safety Committee | Number of quarterly Health and Safety meetings | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | OHS Committee Minutes and attendance registers | Corporate Services
|  |  | MIDT8 | B2B-5 | To ensure effective and efficient ICT Management | Time taken to repair system outage | Number of reports on hours taken to repair the system outage , applications or network to full functionality following a failure | New | New | New | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Reports on hours taken to repair the system, applications or network | Corporate Services
[6 empty] | Cycle time : Time taken to provide customer support or help ticket | Number of reports required to resolve and provide customer support or help ticket | New | New | New | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Report on the required time needed to provide customer support or help ticket | Corporate Services
[6 empty] | ICT expenditure costs monitored | Number of reports on ICT expenditure costs | New | New | New | 4 | 4 | Achieved | N/A | N/A | R1,943,036 | Institutional | Reports on ICT expenditure | Corporate Services
|  |  | MIDT9 | B2B-5 | To promote healthy lifestyle amongst employees | Wellness programmes implemented | Number of Wellness Programmes implemented | 31-Dec-21 and 30-Jun-22 | 31-Dec-21 and 30-Jun-22 | New | 2 | 1 | Not achieved | The scheduled date of the EAP and wellness programme clashed with the scheduled IDP Forum which was also held on the 15 December 2022 and the key stakeholders indicated that it is the festive season and some officials will not be available during December. | The EAP and wellness initiatives will be implemented in the 2023/2024 FY, by 30/06/2024 | N/A | Institutional | Attendance registers, and report | Corporate Services
|  |  | MIDT10 | B2B-5 | To ensure an effective and efficient Registry Management | Reporting on the Implementation of the Registry File Plan | Number of reports on municipal File Plan implementation | 2022-06-30 | 2022-06-30 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Report on implementation of file plan | Corporate Services
|  |  | MIDT11 | B2B-5 | To ensure that employment equity targets are met | Employment Equity Report submitted to the Department of Labour | Submission of the Employment Equity Report to Department of Labour by 15 January 2023 | 2022-01-15 | 2022-01-15 | N/A | 2023-01-15 | 2023-01-15 | Achieved | N/A | N/A | N/A | Institutional | Acknowledgement of Receipt from the Department of Labour and Employment Equity Report | Corporate Services
|  |  | MIDT12 | B2B-6 | To ensure skills development and training to improve access to economic growth opportunities for marginalized groups within the municipality | Reporting on the number of interns employed as part of the internship programme | Report on the number of interns employed as part of the internship programme by 30/06/2023 | 1 | 1 | N/A | 1 | 1 | Achieved | N/A | N/A | N/A | Institutional | Appointment letters/Contracts of employment and report | Corporate Services
[6 empty] | Training Report on unemployed marginalized group submitted to Department of Labour | Number of reports on the unemployed marginalized group training Report submitted to Department of Labour | 1 | 1 | N/A | 1 | 1 | Achieved | N/A | N/A | N/A | Institutional | Reports on trainings for marginalised group and proof of submission | Corporate Services
NKPA: FINANCIAL VIABILITY AND MANAGEMENT
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN2 | B2B-4 | To ensure that the Departmental Budget is spent according to budget projection | Reporting on the implementation of the budget | Number of budget implementation reports | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Budget Implementation Reports | Corporate Services
[6 empty] | Inputs to Budget and Adjustment Budget submitted | Number of inputs reports on the Budget and Adjustment Budget submitted to finance | New | New | New | 2 | 2 | Achieved | N/A | N/A | N/A | Institutional | Reports with budget inputs | Corporate Services
[5 empty] | To ensure revenue enhancement | Revenue through learners licensing generated | Amount of revenue generated through learners licensing | R1.4M | R4M | N/A | R4,8M | 4869263 | Achieved | N/A | N/A | R4,8M | Institutional | Finance system generated reports and correspondence from the billing office | Corporate Services
[6 empty] | Revenue through Motor Licensing generated | Amount of revenue generated through Motor licensing | R1.2M | R2.3M | N/A | R2.4M | 3257273 | Achieved | N/A | N/A | R2.4M | Institutional | Finance system generated reports and correspondence from the billing office | Corporate Services
NKPA: GOOD GOVERNANCE
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1 | B2B-3 | To implement and maintain effective enterprise risk management system | Update and Report on the Risk Management Register | Number of risk management Registers Submitted to MANCO | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Risk Register and MANCO minutes and registers | Corporate Services
|  |  | GG4 | B2B-3 | To transform the municipality into a performance driven institution | Number of Full Council meetings held | Number of full council meetings held | 11 | 11 | N/A | 11 | 11 | Achieved | N/A | N/A | N/A | Institutional | Minutes and Attendance registers | Corporate Services
[6 empty] | Number of EXCO meetings held | Number of EXCO meetings held | 11 | 9 | 2 | 11 | 12 | Achieved | N/A | N/A | N/A | Institutional | Minutes and Attendance registers | Corporate Services
[6 empty] | Coordinate Meetings for 4 Portfolio Committees (Finance Committee, Infrastructure, Community services Portfolio, Corporate Services Portfolio) | Number of Portfolio Committees meetings held | 16 (4 meetings per committee per quarter) | 16 (4 meetings per committee per quarter) | N/A | 16 Portfolio meetings held (4X Finance 4X Corporate 4X Community 4X Infrastructure) | 29 Portfolio meetings held 10 X Finance 8 X Corporate 4 X Community 7 X Infrastructure | Achieved | N/A | N/A | N/A | Institutional | Minutes and Attendance registers | Corporate Services
[6 empty] | Functional MPAC and LLF Committees | Number of MPAC and LLF Committee meetings held | 8 meetings per year | 2 meetings per quarter | N/A | 4 MPAC and 4 LLF Committee meetings held | 7 x MPAC 3 X LLF | Not Achieved | LLF did not meet in Q1 which was due to the unavailability of members | The LLF schedule of meetings will be sent to all members, by 30/09/2023, in the 2023/2024 FY | N/A | Institutional | Minutes and Attendance registers | Corporate Services
|  |  |  | B2B-2 |  | Performance Reports on achieved and not achieved targets submitted to PMS Unit | Performance Reports Submitted to PMS Unit | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | PMS Reports and Submission register | Corporate Services
|  |  | GG9 | B2B-3 | To ensure that services provided to the municipality by the service providers is of high quality | Assess and Report on Service Providers Performance | Number of Reports on the assessment of service providers | 2 | 2 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on Service provider performance | Corporate Services
KEY PERFORMANCE AREA : CROSS CURRING ISSUES
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC1 | B2B-2 | To ensure strategic development and management of the municipality’s Integrated Development Plan | Coordinate the IDP Representative Forum meetings | Number of IDP Representative Forum meetings | 2 | 2 | N/A | 2 | 3 | Achieved | N/A | N/A | N/A | Institutional | Minutes and Attendance registers | Corporate Services
|  |  | CC5 | B2B-2 | To enhance public safety control mechanisms | Update and report on Access control | Number of reports on security management | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports | Corporate Services
ORGANISATIONAL SCORECARD FOR 2022/23
COMMUNITY SERVICES DEPARTMENT
ANNUAL PERFORMANCE REPORT 2022/2023
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | BACKLOG | ANNUAL TARGET 2022/2023 |  | ACHIEVED/NOT ACHIEVED | REASONS FOR NON-ACHIEVEMENT | MEASURES FOR IMPROVEMENT | BUDGET | WARD INFORMATION | MEANS OF VERIFICATION (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | B2B REF N0. |  |  |  |  | 2021/2022 |  | TARGET | ACTUAL
NKPA: BASIC SERVICE DELIVERY
KEY PERFORMANCE AREA: BASIC SERVICE DELIVERY | OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES | OUTCOME 6: AN EFFICIENT, COMPETITIVE AND RESPONSIVE ECONOMIC INFRASTRUCTURE NETWORK | BSD2 | B2B_2 | To Ensure a Safe & Healthy Environment | Reduce waste transferred to Landfill through use of ward-based central waste sorting and disposal areas managed through EPWP and CWP Programmes | Tons of Waste collected Weekly from Wards 3, 4 & 6 | Less than 572 Tons | 533.61tons | N/A | 686 Tons | 707.54 Tons | Not Achieved | There are still recyclables going to the landfill due to some households and largely businesses that are still not separating/ sorting their waste at source for recycling purposes. | Awareness campaigns and engagements will also target businesses starting from Quarter 2 of 2023/24 | R785 000.00 | Institutional | Weekly collection schedule, Analysis report of Msunduzi Landfill site slips | Community Services
[6 empty] | Reporting on the Clean up Campaigns conducted as per the Municipality's Integrated Waste Management Plan | Number of reports on Community based and schools based clean up programme | 16 | 22 | N/A | 4 | 4 | Achieved | N/A | N/A |  | Institutional for all wards | Reports with pictures | Community Services
[6 empty] | Reporting on the number of households with access to basic level of solid waste removal | Number of reports on households with access to basic level of solid waste removal | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A |  | Institutional | Report on waste removal and Billing reports | Community services
[6 empty] | Reporting on the green projects conducted as per the Municipality's Integrated Waste Management Plan | Green Projects: Number of Waste Transfer Stations for waste sorting (SMMEs – Youth & LED – Exit for GGD) | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A |  | Ward 3, 4 and 6 | WMO Report and pictures | Community Services
[7 empty] | Green Projects: Number of Municipal Recycling Projects (SMMEs – Youth & LED – Exit for GGD) | 3 | 3 | N/A | 3 | 3 | Achieved | N/A | N/A |  | Ward 3,4,1 | WMO Report and pictures | Community Services
[5 empty] | To ensure provision of free Basic Services for indigent residents of Mkhambathini Municipality | Reporting on social relief support provided to indigent families | Number of reports social relief packs issued to indigent households monthly | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Ward 1,2,3,4,5,6,7 | Report on social relief support | Community services
[6 empty] | Reporting on the number of households earning less than R1,100 a month with access to free basic Electricity | Number of reports on the number of households earning less than R1,100 a month with access to free basic Electricity | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Ward 1,2,3,4,5,6,7 | Eskom Free Basic Electricity report | Community services
NKPA: MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT11 | B2B_5 | To ensure skills development and training to improve access to economic growth opportunities for marginalized groups within the municipality | Public Employment Programmes job opportunities created | Number of work opportunities created through EPWP (static after Q1 recruitment) | 150 | 150 | N/A | 300 | 341 | Achieved | N/A | N/A | R2 300 000.00 | Ward 1,2,3,4,5,6,7 | EPWP Programmes List of beneficiaries | Community Services
[6 empty] | Training, evaluation and reporting of EPWP workers | Number of training programmes for EPWP workers | 4 | 1 | 3 | 1 | 0 | Not Achieved | The first training was the induction which was postponed due to delays in recruitment processes in Q1 | The training programmes for EPWP workers will resume in Q1, by 30/09/2023, in the 2023/2024 FY |  | Institutional | Training schedule and attendance registers | Community Services
[7 empty] | Number of quarterly EPWP evaluation reports submitted to Public Works | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A |  | Institutional | Quarterly evaluation reports and Proof of submission of Evaluation Reports to Public Works | Community Services
[6 empty] | Reporting on Skills development and training for out of school youth | Number of Reports on out of school youth trained | 70 | 64 | 6 | 1 | 1 | Achieved | N/A | N/A |  | Institutional | Reports on out of school youth trained through EPWP programmes | Community Services
NKPA: LOCAL ECONOMIC DEVELOPMENT
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT | OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME | OUTCOME 4: DECENT EMPLOYMENT THROUGH INCLUSIVE GROWTH | LED1 | B2B-1 | To support Municipality's Rural and Agricultural Development initiatives | Monitor and report on the performance of rural development projects, Agricultural Projects and Livestock and crop Farmers | Number of Agricultural Projects supported in all wards | 70 | 71 | N/A | 30 | 30 | Achieved | N/A | N/A | R300 000.00 | All 7 Wards | List of projects, Report and pictures | Community Services
[7 empty] | Number of reports on Livestock and crop Farmers Trained | 4 | 4 | N/A | 2 | 1 | Not Achieved | Livestock and crop Farmers training was postponed due to financial constraints which were to be revisited in Q3 after the adjustment budget. | The livestock training programme will resume in Q 2 of 2023/.2024. |  | All wards represented | Training schedule, Training registers and reports | Community Services
[6 empty] | To launch the LED Forum | Date of LED Forum Launch | 2023-06-30 | Not achieved | To ensure the launch of the LED Forum as per the set date | 2023-05-30 | Not Achieved | Not Achieved | The processes for establishment of the LED forum commenced. The subforums were all established and due to technical issues the establishment of the Forum was delayed for clarity. | The LED Forum Launch will be done by 30 March 2024 | R220 000.00 | Institutional (open to all wards) | Registers, reports and pictures | Community Services
|  |  | LED2 |  | To develop and support all emerging SMMEs and Cooperatives within the municipality | SMME & Cooperatives support and training programme implemented | Quarterly reports on SMME & Cooperatives support and training programmes implemented | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A |  | Institutional | LED Manager's Report | Community Services
|  |  | LED6 |  | To promote tourism within the municipal area | To coordinate tourism promotion activities | Date of tourism brochure approved by Council | 2022-06-30 | 2021-10-21 | N/A | 2023-06-30 | Not Achieved | Not Achieved | Review of the tourism brochure was postponed to the beginning of the new financial year as focus was shifted to the tourism route. The brochure will be reviewed after a meeting with local tourism businesses. | The review of the tourism brochure will be concluded by Q1 , 30 September 2023 of the 2023/2024 financial year | R150 000.00 | Institutional (open to all wards) | Council resolution and reviewed brochure | Community Services
[7 empty] | Report on Mkhambathini Tourism Route Launch | 2022-03-31 | 2022-03-31 | N/A | 1 | 1 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
|  |  | LED5 |  | To promote Arts and Culture Activities | Coordinate crafters development programme through training/ workshops | Number of Activities implemented as part of establishment of the Azibuye Emasisweni Girls programme | New | New | N/A | 2 | 2 | Achieved | N/A | N/A | 1208500 | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Number of Activities implemented as part of establishment of the Azibuye Emasisweni Boys programme | 2022/05/30 (Date of “Azibuye Emasisweni” Cultural Knowledge workshops for young boys) | 2022/05/21 (Date of “Azibuye Emasisweni” Cultural Knowledge workshops for young boys) | N/A | 2 | 1- Boys' Camp and 1 Boys Workshop (2) | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Date of Mkhambathini Cultural Event | New | New | New | 2022-12-31 | 2022-12-04 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Number of artist and crafters development workshops | 4 | 5 | N/A | 4 | 0 | Not Achieved | The artist and crafters development workshops was not done due to the delayed efforts to align the programmes with DSAC in order to reduce the costs if any | The artist and crafters development workshop will be done in partnership with DSAC and local CBO by Q2 of the 2023/2024 financial year. |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
|  |  | LED3 |  | To promote the rights of vulnerable groups through various socio-economic development programmes | Coordinate and hold Youth Council Meetings | Number of Youth Council Meetings | New | New | New | 4 | 1 | Not Achieved | The youth Council meeting could not convene due to unavailability of members. The new members are working and can only meet on weekends. | The Youth Council Meetings will as at Q1 of 2023/2024 happen on weekends to ensure that members are able to make the meeting. | R3 870 000.00 | Institutional (open to all wards) | Registers, minutes | Community Services
[6 empty] | Youth Programmes implemented | Date of Annual Career Exhibition for youth in and out of school | Quarter 1 – 31 August 2021 (Out) Q4 – 31 May 2022 (In) | Not achieved | To ensure Annual Career Exhibition is conducted as per set date | 2023-05-31 | 17 May and 24 June 2023 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Dates of Annual Matric Exam Prayers for Mkhambathini and Mid-Illovo Circuits | 2022-10-31 | 20-21 October 2022 | N/A | 2023-10-31 | 2023-10-27 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Date of Annual Mkhambathini Schools Achievement Awards | 2022-02-28 | 2022-02-11 | N/A | 2023-02-28 | 2023-02-09 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[6 empty] | Coordinate programmes for people living with Disability | Number of Quarterly Disability Awareness Campaigns | 4 | 3 | 1 | 4 | 1 | Not Achieved | The Disability Awareness campaign was rescheduled due to the unavailability of the Disability Forum | The campaign will take place in July 2023 (new financial year). |  | Institutional (open to all wards) | Report and pictures | Community Services
[7 empty] | Date of “Disability Mayoral Games” | New | New | New | 2023-06-30 | 2022-10-23 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Report and pictures | Community Services
[7 empty] | Date of Disable persons attending the “Annual Disability Imbizo” | New | New | New | 2022-12-31 | 2022-12-06 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Attendance Registers and pictures | Community Services
[6 empty] | Coordinate gender based activities | Date of Men’s Dialogues in all wards | 2021-10-31 | 2021-10-06 | N/A | 2023-06-30 | 2022-08-13 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Attendance Registers and pictures | Community Services
[7 empty] | Date of Women’s Dialogues in all wards | 2021-10-31 | 2021-10-05 | New | 2023-06-30 | 2023-05-20 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Attendance Registers and pictures | Community Services
[6 empty] | Coordinate platforms for senior citizens engagements and dialogues | Date of Senior Citizen’s Dialogues in all wards | 2021-08-01 | Not achieved | To ensure the Senior Citizens event is conducted as per set date | 2022-08-03 | Not Achieved | Not Achieved | The dialogue was postponed due to a clash with the Senior Citizens Golden games programme. | The dialogues programme will resume in the new financial year 2023/2024 after collaboration with DSD - by 30 March 2024. |  | Institutional (open to all wards) | Attendance Registers and pictures | Community Services
[6 empty] | Coordinate participation in the Golden games by senior citizens of Mkhambathini Municipality | Date of “Local Golden Games Sports Day” | 2021-07-01 | Not achieved | To ensure the Local Golden Games sports day is conducted as per set date | 2022-08-03 | 2022-08-03 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Report and pictures | Community Services
[6 empty] | Coordinate and host Senior Citizens event through Operation MBO | Date of Senior Citizens event Coordinated and hosted through Operation MBO | 2021-12-31 | 2021-12-08 | N/A | 2022-12-31 | 2022-12-07 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Attendance Registers and pictures | Community Services
|  |  | LED4 |  | To promote Sports and Recreation | Coordinate participation in the Annual Mayoral games and participation in the Annual District Games | Date of Annual Mayoral Games and participation in the Annual District Games | 2022-06-30 | Not Achieved | To ensure the Annual Mayoral Games and participation in the Annual District Games is conducted as per set date | 2022-12-31 | 2022-10-22 | Achieved | N/A | N/A | R1 680 000.00 | Institutional (open to all wards) | Report and pictures | Community Services
[6 empty] | Sports Coaching workshops implemented and tournaments held | Number of Sports Coaching workshops implemented | 1 | 1 | N/A | 2 | 0 | Not Achieved | The delays in the sports coaching plan were due to the unavailability of the sports confederation. | 1 workshops was held in Q4. Sports Coaching workshops, will resume in Q2 of 2023/2024 FY after the sports indaba |  | Institutional (open to all wards) | Attendance Registers and pictures | Community Services
|  |  | LED8 | B2B-1 | Ensure implementation of Operation Sukuma Sakhe and special programmes | Ensure functional OSS Task team (LTT) | Number of OSS Local Task Team Meetings | 4 | 3 | 1 | 4 | 3 | Not Achieved | OSS Local Task Team Meetings was postponed due to public service week, in Q1 | OSS Local Task Team Meetings will resume in Q1 of 2023/2024 FY | R170 000.00 | Institutional (open to all wards) | Attendance registers and minutes | Community Services
|  |  | LED5 | B2B-1 | Coordinate and hold a life skills, workshops and programmes aimed at reducing teenage pregnancy, substance abuse and HIV/AIDS infections amongst teenagers and youth/any new pandemic | Coordinate and hold Local Aids Council Meetings | Number of Local Aids Council Meetings | 4 | 4 | N/A | 4 | 3 | Not Achieved | Local Aids Council Meetings was postponed due to public service week, in Q1 | Local Aids Council Meetings will resume in Q1 of 2023/2024 FY | R340 000.00 | All 7 Wards | Minutes and registers | Community Services
[6 empty] | Coordinate and hold a life skills workshops for youth, Parenting workshops for young mothers, teenager health mentors and Families Matter Workshops | Number of Life skills Workshops for youth in schools (Ikusasa-lakho) | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Number of Parenting Workshops for young mothers | 3 | 3 | N/A | 2 (Q1&3) | 2 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Number of teenage health mentors Selected | 7 | Not Achieved | 7 | 7 | 25 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
[7 empty] | Number of Families Matter Workshops | 2 (1&3) | 2 (1&3) | N/A | 2 (1&3) | 2 | Achieved | N/A | N/A |  | Institutional (open to all wards) | Registers, photos, reports | Community Services
NKPA: FINANCIAL VIABILITY AND MANAGEMENT
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN7 | B2B_4 | To ensure effective and efficient grants management | Spend 100% of the EPWP allocation | Percentage spent on EPWP allocation (accumulative) | 100% | 100% | N/A | 100% | 100% | Achieved | N/A | N/A | 1 329 000.00 | Institutional | Reports submitted to Public Works | Community Services
NKPA: GOOD GOVERNANCE
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1 | B2B-3 | To implement and maintain effective enterprise risk management system | Update and Report on the Risk Management Register | Number of risk management Registers Submitted to MANCO | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Risk Register and MANCO minutes and registers | Community Services
|  |  | GG4 | B2B_3 | To transform the municipality into a performance driven institution | Performance Reports on achieved and not achieved targets submitted to PMS Unit | Performance Reports Submitted to PMS Unit | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | PMS Report and Submission register | Community Services
|  |  | GG9 | B2B-3 | To ensure that services provided to the municipality by the service providers is of high quality | Assess and Report on Service Providers Performance | Number of Reports on the assessment of service providers | 2 | 2 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on Service provider performance | Community Services
NKPA: CROSS CUTTING
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC5 | B2B_2 | To ensure a functional Disaster Management Unit | Disaster Management Plans Developed and approved | Date of approval of the Disaster Management Plan review | 2022-06-30 | 2022-06-29 | N/A | 2023-06-30 | 2023-05-31 | Achieved | N/A | N/A | R950 000.00 | Institutional for All Wards | Council resolution and Disaster Management plan | Community Services
[7 empty] | Date of approval of the Disaster Management Seasonal Sector Plans review | 2021-09-30 | Not Achieved | To ensure the approval of the Disaster Management Seasonal Sector Plans review is conducted as per set date | 30 September 2022 31 March 2023 | Not achieved | Not achieved | The seasonal plan was prepared and not sent to Council due to the portfolio committee meeting being postponed. (since Council reports start at portfolio meetings) | The Disaster Management Seasonal Sector Plan will be presented to Portfolio Committee of Quarter 1, 2023/2024 |  | Institutional | Council resolution and seasonal plans | Community Services
|  |  |  | B2B_2 |  | Ensure a functional Disaster Management Advisory Forum | Number of Disaster Management Forum Meetings | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A |  | Institutional | Attendance registers, minutes | Community Services
ORGANISATIONAL SCORECARD FOR 2022/23
FINANCIAL SERVICES DEPARTMENT
ANNUAL PERFORMANCE REPORT 2022/2023
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | BACKLOG | ANNUAL TARGET 2022/2023 |  | ACHIEVED/NOT ACHIEVED | REASONS FOR NON-ACHIEVEMENT | MEASURES FOR IMPROVEMENT | BUDGET | WARD INFORMATION | MEANS OF VERIFICATION (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | B2B REF N0. |  |  |  |  | 2021/2022 |  | TARGET | ACTUAL
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT6 | B2B_4 | To ensure effective and efficient asset management | Fixed Asset Register reconciliation performed and signed of by the Finance Manager | Number of Monthly reports on Fixed Asset Register reconciliation | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Reports signed by the Finance Manager | Chief Financial Officer
|  |  | MIDT7 | B2B-5 | To ensure that efficient and effective fleet management | Monthly fuel reconciliation reports | Number of ,monthly fuel reconciliation reports | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Fuel reconciliation reports and statements | Chief Financial Officer
[6 empty] | Fleet management reports to portfolio committee | Number of Fleet management reports submitted to portfolio committee | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Fleet management reports, portfolio minutes and attendance registers | Chief Financial Officer
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT | OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME | OUTCOME 4: DECENT EMPLOYMENT THROUGH INCLUSIVE GROWTH | LED9 | B2B-1 | To Promote emerging Businesses | Increase number of Award made to BBBEE level 1 companies for bids more than R30 000. | No. of bids above R30 000 awarded to BBBEE level 1 companies | 40 | 40 | N/A | 30 | 26 | Not Achieved | There were only 8 transactions for in Quarter 1 | Target will be reviewed in the new FY 2023/2024, by Q1, 30/09/2023 | N/A | Ward 1,2,3,4,5,6,7 | Schedule of awards and copy of purchase order | Chief Financial Officer
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN1 | B2B_4 | To ensure enforcement of sound financial management practices | Develop and Implement the Departmental Procurement Plan to ensure timeous procurement of required goods and services | Date the procurement plan inputs is submitted to Portfolio Committee and Treasury | 2022-05-31 | 2022-05-31 | N/A | 2023-05-31 | 2023-03-31 | Achieved | N/A | N/A | N/A | Institutional | Procurement plan, portfolio minutes, acknowledgement from Treasury | Chief Financial Officer
[6 empty] | Convening of BEC within 15 days after the closing date of an advert | Number/Cycle of days of BEC meetings held after closing date of an advert | 15 days | Not Achieved | To ensure BEC meetings are held 15 days after closing date of an advert | 15 days | Not Achieved | Not Achieved | Due to the unavailability of the committee the meeting did not convene | The Committee will revise a schedule of meetings for the year and circulate to all members, will be done by Q1 of the 2023/2024 FY by 30/09/2023 | N/A | Institutional | BEC minutes, attendance registers and advert | Chief Financial Officer
[6 empty] | Convening of BAC within 14 working days after the BEC meetings | Number/Cycle of days of BAC meetings held after the BEC processes | 14 days | Not Achieved | To ensure BAC is held within 14 working days after the BEC meetings | 14 days | Not achieved | Not achieved | Due to the unavailability of the committee the meeting did not convene | The Committee will revise a schedule of meetings for the year and circulate to all members, will be done by Q1 of the 2023/2024 FY by 30/09/2024 | N/A | Institutional | BAC minutes and BEC minutes and attendance register | Chief Financial Officer
|  |  | FIN2 | B2B_4 | To ensure that the Budget is spent according to budget projection | % of the capital budget actually spent on capital projects | % Spent (Total spending on capital projects / Total capital budget) x 100 on capital projects | 100% | 100% | N/A | 100% | 100% | Achieved | N/A | N/A | N/A | Institutional | MIG Implementation Plan and proof of payments | Chief Financial Officer
|  |  | FIN3 | B2B_5 | To ensure compilation of a credible Annual Financial Statements | AFSs submitted to AG by 31 August 2022 | Date the AFS is submitted to Auditor General | 2021-08-31 | 2021-11-30 | N/A | 2022-08-31 | 2022-08-31 | Achieved | N/A | N/A | N/A | Institutional | AFS and proof of receipt from the Office of the Auditor General | Chief Financial Officer
[6 empty] | Municipal Manager to monitor the preparation of Annual Financial Statements to ensure credibility in order for the municipality to receive an unqualified report | , Municipal Manager to ensure that the municipality receives unqualified report by the set date | 2021-11-30 | 2021-12-31 | N/A | 2022-12-31 | 2022-11-18 | Achieved | N/A | N/A | N/A | Institutional | Auditor Generals Reports | Chief Financial Officer
|  |  | FIN4 | B2B_4 | To ensure revenue enhancement | Development and approval of a revenue enhancement strategy | Date of revenue enhancement approval | 2022-06-30 | 2022-05-26 | N/A | 2023-06-30 | 2023-05-31 | Achieved | N/A | N/A | N/A | Institutional | Revenue enhancement Strategy | Chief Financial Officer
[6 empty] | Quarterly Age Analysis reports prepared and submitted to Council | Number of Age Analysis reports submitted to Council | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports and council resolution | Chief Financial Officer
[6 empty] | Increased percentage of Debts collection rate | Percentage of Debt collection: Amount collected | 70% | 101% | N/A | 85% | 89% | Achieved | N/A | N/A | N/A | Institutional | Reports | Chief Financial Officer
|  |  | FIN5 | B2B_4 | To ensure that the Municipal Liquidity position is managed at 1:10 | Prepare quarterly reports on the cost coverage ratio [All available cash at a particular time) + (Investments)- Conditional grants)]/ Monthly fixed operating expenditure) | Quarterly cost coverage ratio reports submitted to Council on cost coverage ratio | 1:10 | 1:11 | N/A | 1:10 | 1:10 | Achieved | N/A | N/A | N/A | Institutional | Reports and council resolution | Chief Financial Officer
|  |  | FIN6 | B2B_4 | To ensure effective management of the payroll system | Prepare and submit monthly Payroll Reconciliation to Senior Management | Number of monthly Payroll Reconciliation reports submitted to senior managers within 7 days after pay day | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Reports signed by the Finance Manager | Chief Financial Officer
|  |  | FIN7 | B2B_4 | To ensure effective and efficient grants management | Prepare and submit monthly Reconciliation of grants income | Number of monthly reports on Reconciliations of grants income signed off by the Finance Manager | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Reports and signed proof of receipt by managers | Chief Financial Officer
[6 empty] | Prepare and submit financial reports on EPWP allocation spending | Number of financial reports on % Spent on EPWP allocation submitted to Public Works | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Report and proof of submission (email correspondence copy) | Chief Financial Officer
|  |  | FIN8 | B2B_4 | To improve reporting Management | Preparation of quarterly report to Council (Section 52d of MFMA) | Number of reports submitted to Council | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Section 52 (d) report and Council resolution | Chief Financial Officer
[6 empty] | Prepare monthly Vat Reconciliations | Number of monthly Vat Reconciliations prepared and signed by the Finance Manager | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Reports signed by the Finance Manager | Chief Financial Officer
|  |  | FIN9 | B2B_4 | To ensure effective and efficient supply chain management system | Submit Financial reports to the Finance Portfolio Committee on a quarterly basis | Number of Finance report submitted to Finance Committee | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
[6 empty] | Ratio for cost coverage | Debt coverage Ratio: Total operational revenue less operational grants/ debt service payment due within the financial year | 1:01 | 1:01 | N/A | 1:01 | 1:01 | Achieved | N/A | N/A | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
[7 empty] | Outstanding service debtors to revenue ratio: Total outstanding service debtors divide by annual revenue from services | 1:01 | 1:01 | N/A | 1:01 | 1:01 | Achieved | N/A | N/A | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
[7 empty] | Costs coverage ratio:((available cash less unspent conditional grants-overdraft) plus short term investments) divided (by monthly fixed operating expenditure less depreciation, amortization, prove for bad debts, impairment and loss of disposal of assets) | 1:7 | 1:10 | N/A | 1:7 | 1:09 | Achieved | N/A | N/A | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
[6 empty] | Prepare and submit monthly Bank Reconciliations signed by the Finance Manager | Number of monthly bank reconciliation | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Monthly reconciliations signed by the Finance Manager | Chief Financial Officer
[6 empty] | Prepare and submit monthly Creditors Reconciliations signed by the Finance Manager | Number of monthly Creditors Reconciliation and Age Analysis | 12 | 12 | N/A | 12 | 12 | Achieved | N/A | N/A | N/A | Institutional | Age analysis and Monthly reconciliations signed by the Finance Manager | Chief Financial Officer
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1 | B2B_3 | To implement and maintain effective enterprise risk management system | Update and reports on the Risk Management Register | Number of Risk Management registers submitted to MANCO | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Risk Register and MANCO minutes and registers | Chief Financial Officer
|  |  | GG10 | B2B_3 | To transform the municipality into a performance driven institution | Performance Reports on achieved and not achieved targets submitted to PMS Unit | Number of Performance Reports submitted to PMS Unit | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | PMS Report and Submission register | Chief Financial Officer
|  |  | GG9 | B2B-5 | To ensure that services provided to the Municipality by service providers is of high quality | Assess and reports on Service Providers Performance | Number of reports on the assessment of Service Providers | 2 | 2 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on Service provider performance | Chief Financial Officer
|  |  | GG8 | B2B_3 | To provide reasonable assurance on the adequacy and effectiveness of internal control system | Development and management of an Audit Action plan to maintain a good audit opinion | Report on Audit Action plan submitted to Council | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports and Council Resolution | Chief Financial Officer
KEY PERFORMANCE AREA : CROSS CURRING ISSUES
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC1 | B2B_2 | To ensure strategic development and management of the municipality’s Integrated Development Plan | Development and approval of the IDP/ Budget Process Plan | Date of adoption of the 2023/2024 IDP/ Budget Process Plan | 2021-08-31 | 2021-08-26 | N/A | 2022-08-31 | 2022-08-31 | Achieved | N/A | N/A | N/A | Institutional | Process plan and Council Resolution | Chief Financial Officer
[6 empty] | Coordinate the IDP Representative Forum meetings | Number of IDP Representative Forum meetings | 2 | 2 | N/A | 2 | 2 | Achieved | N/A | N/A | N/A | Institutional | Attendance registers and/or minutes | Chief Financial Officer
[6 empty] | Adoption and Implementation of the Integrated Development Plan (IDP) focusing on delivery of 10 critical municipal services | Date of adoption of the 2023/2024 IDP | 2022-06-30 | 2022-06-29 | N/A | 30 June 2023 (Final adoption) | 2023-05-31 | Achieved | N/A | N/A | N/A | Institutional | Q2 Mayoral outreach Programme Attendance Registers and minutes , Q3 Draft IDP Council Resolution, Q4 Final IDP Council Resolution | Chief Financial Officer
ORGANISATIONAL SCORECARD FOR 2022/2023
TECHNICAL SERVICES DEPARTMENT
ANNUAL PERFORMANCE REPORT 2022/2023
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | BACKLOG | ANNUAL TARGET 2022/2023 |  | ACHIEVED/NOT ACHIEVED | REASONS FOR NON-ACHIEVEMENT | MEASURES FOR IMPROVEMENT | BUDGET | WARD INFORMATION | MEANS OF VERIFICATION (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | B2B REF N0. |  |  |  |  | 2021/2022 |  | TARGET | ACTUAL
NKPA: BASIC SERVICE DELIVERY
KEY PERFORMANCE AREA: BASIC SERVICE DELIVERY | OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES | OUTCOME 6: AN EFFICIENT, COMPETITIVE AND RESPONSIVE ECONOMIC INFRASTRUCTURE NETWORK | BSD1 | B2B_1 | To ensure the provision, upgrade and construction of infrastructure and services that enhance socio economic development within the municipality | Ezinembeni Electrification | Number of household electrified but not energised (accumulative) | 343 | 0 | 343 | 343 | 0 | Not Achieved | After site establishment and delivery of material on site, 8 transformers were stolen and of which a case was open with the local SAPS regarding the stolen transformers. This delayed the project timeframes and affected two different projects. Further to this, the service provider continued to implement the project of which MV and LV lines have been connected (including stringing of lines). | Dry connections in households will be done in Q1 of 2023/2024 for all 343 H/H. | 8232000 | Ward 5 | Report / Completion Confirmation Register | Technical Services
[6 empty] | Mkhambathini Electrification | Number of household electrified but not energised (accumulative) | 78 | 0 | 78 | 78 | 0 | Not Achieved | After site establishment and delivery of material on site, 8 transformers were stolen and of which a case was open with the local SAPS regarding the stolen transformers. This delayed the project timeframes and affected two different projects. Further to this, the service provider continued to implement the project of which MV and LV lines have been connected (including stringing of lines). | Dry connections in households will be done in Q1 of 2023/2024 for all 78 H/H. | 1878000 | Ward 5 | Report / Completion Confirmation Register | Technical Services
[6 empty] | Nkanyezini-Mboyi | Number of household electrified but not energised (accumulative) | New | New | New | 292 | 149 | Not Achieved | Due to financial constraints, the project was revised to 2 phases so half can be done to ensure that the rest of the project can be accommodated in the 2023/2024 budget. | Phase 2 (143) connections will be implemented by 30 June 2024. | 7000000 | Ward 3 | Report / Completion Confirmation Register | Technical Services
[6 empty] | Mgwenya-gulube Electrification | Number of household electrified but not energised (accumulative) | New | New | New | 320 | 243 | Not Achieved | The project was implemented and required additional funding which was only confirmed in March 2023 which affected the completion. | The project will resume in Q1 of the 2023/2024 FY | 13800000 | Ward 7 | Report / Completion Confirmation Register | Technical Services
[6 empty] | Banqobile Sport Field | Percentage of Banqobile Sport Field completed (accumulative) | 100% | 68% | 32% | 80% | 90% | Achieved | N/A | N/A | 8000000 | Ward 5 | Progress Report | Technical Services
[6 empty] | Mgwaphuna Access Road | Percentage of Mgwaphuna Access Road of 3,5 kms completed by 30 June 2023 (accumulative) | New | New | New | 100% | 100% | Achieved | N/A | N/A | 8763661.58 | Ward 4 | Report / Practical Completion Certificates | Technical Services
[6 empty] | Makhokhoba Access Road / Bridge | Percentage of Makhokhoba Access Road /Bridge of 0,5 kms completed by 30 June 2023(accumulative) and Bridge | New | New | New | 60% | 65% | Not Achieved | The late approval of the EIA and the plant breakdown on site resulted to the delay in the completion of project. | Intervention from the office of the Municipal Manager including the review of the Project plan and AFA application to COGTA to ensure that the project is finalised before 30 November 2023. | 3600000 | Ward 3 | Progress Report | Technical Services
[6 empty] | Jilafohlo Access Road | Percentage of Jilafohlo Access Road of 4,5 kms completed by 30 June 2023 (accumulative) | 100% | 78% | 22% | 80% | 80% | Not Achieved | The contractor abandoned the site after they reported to the municipality that the subcontrator for the concrete could not assist them due to terrain. | The negotiations between the contractor and the municipality was concluded and which resulted to mutual termination of the contract to allow the municipality to engage a service provider who will assist in finalising the project before 30 November 2023. | 6200000 | Ward 7 | Progress Report | Technical Services
[6 empty] | Chibini Access Road | Percentage of Mgwaphuna Access Road of 1,5 kms completed by 30 June 2023 (accumulative) | New | New | New | 60% | 60% | Achieved | N/A | N/A | 3000000 | Ward 2 | Progress Report | Technical Services
[6 empty] | Maqongqo Taxi Rank | Percentage of Maqongqo Taxi Rank completed (accumulative) | New | New | New | 40% | 20% | Not Achieved | The Maqongqo Taxi Rank project has been put on hold due to land ownership dispute . | The negotiations between the said land owner, the municipality and the Maphumulo Traditional authority are ongoing and new targets can only be set once the negotiations are finalised. | 3000000 | Ward 1 | Progress Report | Technical Services
|  |  | BSD3 | B2B_2 | To ensure that the municipal infrastructure assets are maintained | Maqongqo Community Hall | Percentage of Maqongqo Community Hall completed (accumulative) | New | New | New | 100% | 100% | Achieved | N/A | N/A | 700000 | Ward 1 | Report / Practical Completion Certificates | Technical Services
[6 empty] | Ophokweni Access Road | Percentage completion of Ophokweni Access Road of 2,5kms by 30 June 2023 (accumulative) | 100% | 100% | N/A | 100% | 100% | Achieved | N/A | N/A | 700000 | Ward 2 | Report / Practical Completion Certificates | Technical Services
[6 empty] | Mboyi Access Road | Percentage completion of Mboyi Access Road of 1,7kms by 30 June 2023 (accumulative) | New | New | New | 100% | 100% | Achieved | N/A | N/A | 700000 | Ward 3 | Report / Practical Completion Certificates | Technical Services
[6 empty] | Mahleka Sports field | Percentage of Mahleka Sportfield completed (accumulative) | New | New | New | 100% | 100% | Achieved | N/A | N/A | 700000 | Ward 4 | Report / Practical Completion Certificates | Technical Services
[6 empty] | Qedazulu Access Road | Percentage completion of Qedazulu Access Road of 1,2kmsby 30 June 2023 (accumulative) | New | New | New | 100% | 100% | Achieved | N/A | N/A | 700000 | Ward 5 | Report / Practical Completion Certificates | Technical Services
[6 empty] | F 1503 Access Road | Percentage completion of F 1503 Access Road of 1km by 30 June 2023 (accumulative) | New | New | New | 100% | 74% | Not Achieved | The contractor abandoned the site without completing the work as per appointed scope which resulted in the termination of the contract. | A New contractor will be appointed to complete the remaining scope of work in Q1 of the 2023/2024 FY | 700000 | Ward 6 | Report / Practical Completion Certificates | Technical Services
[6 empty] | Mantugwini Access Road | Percentage completion of Mantugwini Access Road of 1km by 30 June 2023 (accumulative) | New | New | New | 100% | 100% | Achieved | N/A | N/A | 700000 | Ward 7 | Report / Practical Completion Certificates | Technical Services
NKPA: FINANCIAL VIABILITY AND MANAGEMENT
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN7 | B2B_3 | To ensure effective and efficient grants management | Spend 100% of the MIG allocation by End of June 2023 | Percentage spent on MIG allocation (accumulative) | 100% | 100% | N/A | 100% | 100% | Achieved | N/A | N/A | 24755000 | Institutional | Reports submitted to Council | Technical Services
[6 empty] | Prepare and submit progress reports on MIG projects implemented in all wards | Number of progress reports submitted to Council quarterly | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports submitted to Council | Technical Services
[6 empty] | Prepare and submit progress reports on INEP electricity projects implemented in all wards | Number of progress reports submitted to Council quarterly | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | 18000000 | Institutional | Reports submitted to Council | Technical Services
NKPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1 | B2B-3 | To implement and maintain effective enterprise risk management system | Update and Report on the Risk Management Register | Number of risk management Registers Submitted to MANCO | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | N/A | Risk Register and MANCO minutes and registers | Technical Services
|  |  | GG9 |  | To ensure that services provided to the Municipality by service providers is of high quality | Assess and Report on Service Providers Performance | Number of reports on the assessment of service providers | 2 | 2 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Reports on Service provider performance | Technical Services
|  |  | GG10 |  | To transform the municipality into a performance driven institution | Performance Reports on achieved and not achieved targets submitted to PMS Unit | Number of Performance Reports Submitted to PMS Unit | 4 | 4 | N/A | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | PMS Report and Submission register | Technical Services
NKPA: CROSS CUTTING
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC2 | B2B_22 | To ensure spatial development in the entire area of Mkhambathini Municipality | Reporting on SPLUMA applications approved to the Portfolio Committee | Number of reports on SPLUMA applications approved and submitted to the Portfolio Committee | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Spluma Application Report and portfolio minutes and registers | Technical Services
|  |  | CC3 |  | To promote effective and efficient building control services | Reporting on Building Inspections to the Portfolio Committee | Number of reports on building inspections submitted to the Portfolio Committee | 4 | 3 | 1 | 4 | 4 | Achieved | N/A | N/A | N/A | Institutional | Inspection reports / building approvals, portfolio minutes and registers | Technical Services
|  |  | CC6 |  | Coordinate and hold meetings with Developers and the Department of Human Settlement | Reporting on housing development within the municipality to the Portfolio Committee | Number of reports on housing development within the municipality submitted to the Portfolio Committee | 4 | 3 | 1 | 4 | 2 | Not Achieved | The Q1 and Q2 Portfolio Committee meeting did not convene due to another commitment by the committee | The Q1 and Q2 reports were integrated in the Q3 agenda to ensure reporting was done as required. | N/A | Institutional | Implementing Agents' Report / Attendance register, Portfolio Committee Minutes | Technical Services
82.56%
82.56%