## MKHAMBATHINI CEF
PROJECT NO. | PROJECT DESCRIPTION | PROPOSED SPECIFICATIONS | LOCATION | CHALLENGE TO BE ADDRESSED/ KEY ISSUE | LONG-TERM SPATIAL OBJECTIVE | LONG-TERM SPATIAL STRATEGY | TYPE OF PROGRAM/ PROJECT | BENEFICIARIES OF INTERVENTION | ESTIMATED DURATION OF PROJECT | ESTIMATED START AND END DATES | [24 empty] | FUNDS |  |  | PROJECT STATUS | PRIORITY LEVEL | PERCIEVED RISKS TO IMPLEMENTATION/ DEPENDENCIES ON OTHER PROJECTS | MEANS OF MITIGATING PERCIEVED RISKS | APPLICABLE LAND DEVELOPMENT PROCEDURES AND/OR APPLICATIONS | ESTIMATED DATE BY WHEN THE PROCEDURE OR APPLICATION NEEDS TO BE INITIATED
[10 empty] | CURRENT IDP TERM |  |  |  |  | 5 YEARS |  |  |  |  | 10 YEARS |  |  |  |  | 15 YEARS |  |  |  |  | 20 YEARS |  |  |  |  | ESTIMATED BUDGET | ESTIMATED COST OF MAINTAINANCE OVER 10 YEARS | PROPOSED SOURCE OF FUNDING
[10 empty] | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046
INF-01 | Installation of ±15 communal water standpipes | ±15 communal water standpipes | Embo-Thimuni | Lack of access to potable water. | Support Incremental Upgrading of Basic Services. | Promote incremental and appropriate service solutions. | Water | Local community | 3-years | [25 empty] | 3000000 | 500 | Municipality/MIG | 2026: Sourcing of funds | 1 | Water source availability. Availability of budget. | Prioritise clusters near existing supply. Phase installations. Assign local maintenance responsibility. | Nil | NA
INF-02 | Upgrade of existing water supply infrastructure | Repair and replace ageing pipes, install additional communal standpipes, connect underserved clusters, improve pressure and reliability. | Manyavu | Inadequate water supply in densifying settlements. | Support Incremental Upgrading of Basic Services. | Prioritise service upgrades in consolidation areas. | Water | Local community | 5-years | [25 empty] | 4500000 | 1500000 | Municipality/MIG | 2026: Sourcing of funds | 1 | Technical assessment. Sector Department support. Availability of budget. | Conduct rapid infrastructure audit. Package upgrades into small contracts. | Nil | NA
INF-03 | Construction of stormwater channels and erosion control measures | Install side drains, mitre drains, and berms; construct stone-packed check dams and gabions in gullies; provide localised open drainage near homesteads and facilities. | Embo-Thimuni | Flooding and erosion impacting settlements. | Improve Mobility, Access, and Connectivity. | Prioritise road and stormwater upgrades along key routes. | Stormwater | Local community | 5-years | [25 empty] | 3500000 | 500000 | Municipality/MIG | 2026: Sourcing of funds | 1 | Availability of budget. | Target highest-risk areas first. Use labour-intensive, low-cost methods for construction. | Nil | NA
INF-04 | Maintenance and re-gravelling of internal access roads. | Regrade and re-gravel priority internal settlement roads, repair potholes and washed-out sections, shape road camber, and install basic roadside drainage and culverts at critical crossings. | Manyavu | Poor internal road access. | Improve Mobility, Access, and Connectivity. | Improve internal settlement access. | Roads | Local community | 5-years | [25 empty] | 3000000 | 1000000 | Municipality/MIG | 2026: Sourcing of funds | 2 | Availability of budget. | Combine with stormwater improvements project. Implement routine maintenance cycles. | Nil | NA
INF-05 | Installation of high-mast lighting at key community nodes. | Install solar or grid-connected high-mast lighting at identified community nodes such as halls, taxi stops, trading areas, and service points to improve safety, visibility, and evening activity. | Isimahla and Macala-Gwala | Poor safety and visibility at community nodes. | Strengthen Livelihoods and the Local Economy. | Strengthen local service nodes. | Electricity | Local community | 5-years | [25 empty] | 1500000 | 500000 | Municipality/MIG | 2026: Sourcing of funds | 2 | Electricity or solar supply. Municipal maintenance capacity. | Install at active nodes. Use solar units with secure mounting. | Nil | NA
INF-06 | Electricity infill connections to existing households. | Extend low-voltage electricity lines and provide metered household connections within already electrified settlement clusters where households currently remain unserved. | Manyavu | Limited household electricity access. | Support Incremental Upgrading of Basic Services. | Align sector investment planning with spatial priorities. | Electricity | Local community | 5-years | [25 empty] | 4500000 | 2000000 | Municipality/MIG | 2026: Sourcing of funds | 2 | Priorities of Eskom or Municipal electrification program. Availability of budget. | Target densest settlement clusters. Align with Eskom electrification planning. | Nil | NA
INF-07 | Electricity infill connections to existing households. | Extend low-voltage electricity lines and provide metered household connections within already electrified settlement clusters where households currently remain unserved. | Maphumulo | Limited household electricity access. | Support Incremental Upgrading of Basic Services. | Align sector investment planning with spatial priorities. | Electricity | Local community | 5-years | [25 empty] | 4500000 | 2000000 | Municipality/MIG | 2026: Sourcing of funds | 2 | Priorities of Eskom or Municipal electrification program. Availability of budget. | Target densest settlement clusters. Align with Eskom electrification planning. | Nil | NA
INF-08 | Construction of taxi shelters and public transport stopping areas. | Construct simple, durable taxi shelters with seating, signage, and hardened stopping surfaces at key transport nodes along primary access routes. | Isimahla and Maphumulo | Lack of formal public transport stopping points. | Improve Mobility, Access, and Connectivity. | Strengthen public transport connectivity. | Roads | Local community | 5-years | [25 empty] | 1500000 | 500000 | Municipality | 2026: Sourcing of funds | 3 | Coordination with taxi associations. Availibility of budget. Maintenance of structures. | Taxi shelters located along active routes. Utilisation of simple, durable designs. | Nil | NA
INF-09 | Extension of water reticulation to identified densifying settlement clusters. | Extend primary and secondary water pipelines from existing supply lines to densifying settlement clusters, including new communal standpipes, small reservoirs where required, and pressure control measures. | Manyavu and Maphumulo | Increasing pressure on basic water services in consolidated settlements. | Support Incremental Upgrading of Basic Services. | Prioritise service upgrades in consolidation areas. | Water | Local community | 7-years | [25 empty] | 18000000 | 5000000 | MIG | 2026: Sourcing of funds | 1 | Availability of budget. Possible WULA application in terms of potential reservoir - to be confirmed during feasibility/design phases. | Phased implmentation and multi-year budgeting. | To be confirmed during feasibility/design phase | To be confirmed
INF-10 | Upgrade of primary access roads to engineered gravel standard. | Upgrade selected primary rural access roads to engineered gravel standard, including proper road base preparation, drainage structures, culverts, and erosion protection measures. | Macala-Gwala | Poor access between settlements and service centres. | Improve Mobility, Access, and Connectivity. | Prioritise road and stormwater upgrades along key routes. | Roads | Local community | 7-years | [25 empty] | 20000000 | 5000000 | Municipality/MIG | 2026: Sourcing of funds | 1 | Availability of budget. | Upgrade only strategic access routes; use engineered gravel standard | Nil | NA
INF-11 | Development of a formalised public transport interchange/rank. | Development of a formalised public transport interchange/rank. | Isimahla | Inadequate public transport infrastructure. | Improve Mobility, Access, and Connectivity. | Strengthen public transport connectivity. | Roads | Local community | 5-years | [25 empty] | 10000000 | 2000000 | Municipality/MIG | 2026: Sourcing of funds | 2 | Availability of budget. Site allocation. Coordination with transport operators. | Phased implmentation and multi-year budgeting. | Nil | NA
INF-12 | Step-by-step improvement of basic water services in rural settlements. | Roll out decentralised service solutions in underserved areas - including communal standpipes, boreholes, rainwater harvesting systems, solar lighting at nodes, and appropriate on-site sanitation systems. | All TCs | Long-term water insecurity under climate variability. | Support Incremental Upgrading of Basic Services. | Promote incremental and appropriate service solutions. | Water | Local community | 7-years | [25 empty] | 30000000 | 10000000 | Municipality/MIG | 2026: Sourcing of funds | 1 | Ongoing sector funding and technical support. | Phase upgrades. Monitor settlement growth and adjust service demand. | Nil | NA
INF-13 | Repair and upgrade of existing basic service systems. | Repair, replace, or upgrade decentralised water, sanitation, and energy systems based on operational performance, community demand, and maintenance records. | All TCs | High maintenance burden of conventional infrastructure. | Support Incremental Upgrading of Basic Services. | Align sector investment planning with spatial priorities. | Water/ Sanitation/ Electricity | Local community | 7-years | [25 empty] | 20000000 | 8000000 | MIG/ Sector Departments | 2026: Sourcing of funds | 1 | Availability of budget. Availaibility of technical teams. | Phased implementation and multi-year budgeting. Establish maintenance schedules. Use local contractors. | Nil | NA
INF-14 | Maqongqo Reservoir & Reticulation | Construction of a 1 ML reservoir and associated reticulation network to address high rural water backlog | Maqongqo | High rural water backlog and unreliable supply. | Improve equitable water access in rural nodes | Cluster-based rural water strengthening with phased expansion | Water | Local community | 4-years | [25 empty] | 15000000 | 5000000 | WSIG / MIG / UMDM | 2026: Sourcing of funds | 2 | Insufficient upstream supply | Confirm bulk supply capacity before construction | Nil | NA
INF-15 | Rural VIP Toilet Programme (Phase 1–3) | Provision of ventilated improved pit (VIP) toilets across affected rural wards to address sanitation backlog | Ward 1, 2, 4, 5, 6, 7 | Sanitation backlog and environmental health risk | Achieve universal basic sanitation coverage | Phased sanitation rollout aligned with settlement density. | Sanitation | Local community | 5-years | [25 empty] | 25000000 | 5000000 | DWS/ MIG | 2026: Sourcing of funds | 2 | Poor maintenance and pit filling over time | Include long-term desludging plan and community education | Nil | NA
INF-16 | Ngilanyoni Water Scheme | Extension of bulk pipeline and installation of elevated storage tank to improve pressure and reliability within the Njanayoni. | Ngilanyoni | Low pressure and intermittent water supply | Achieve reliable rural water service standards equivalent to primary node | Upgrade underperforming rural schemes through phased bulk reinforcement | Water | Local community | 5-years | [25 empty] | 18000000 | 4000000 | DWS/ MIG | 2026: Sourcing of funds | 2 | Insufficient upstream supply pressure | Confirm upstream bulk capacity before installation | Nil | NA
INF-17 | Mid-Illovo Scheme Extension | Extension of bulk pipeline and installation of elevated storage tank to improve pressure and reliability within the Mid-Illovo | Mid-Illovo | No reliable reticulation in Ward 1; industrial connection constraints | Support local economic activity while expanding rural service access. | Integrate commercial and residential supply upgrades. | Water | Local community | 5-years | [25 empty] | 18000000 | 4000000 | DWS/ MIG | 2026: Sourcing of funds | 2 | Insufficient upstream supply pressure | Confirm upstream bulk capacity before installation | Nil | NA
LED-01 | Basic infrastructure support to informal trading areas. | Provide basic trading infrastructure at selected informal trading sites, including graded platforms, shade structures, water points, refuse bins, and simple storage or stall units. | All TCs | Limited support for informal economic activity. | Strengthen Livelihoods and the Local Economy. | Strengthen local service nodes. | LED | Local community | 5-years | [25 empty] | 3000000 | 1000000 | Municipality/ EDTEA/ COGTA | 2026: Sourcing of funds | 3 | Buy-in from informal traders. Town planning restrictions in terms of Planning By-Laws on the location of formalised stalls etc. | Engagements with informal traders on needs and locations. Engagement with Spatial Planning to identify locational/land development requirements in relation to stalls etc. | Possible SPLUMA | 2027
LED-02 | Pilot implementation of rural markets (2–3 locations). | Establish 2–3 pilot rural market sites with modular trading infrastructure, storage, ablutions, water points, and an operating model for periodic market days linked to local agricultural production. | Manyavu and Isimahla | Limited local economic opportunities beyond informal trading. | Strengthen Livelihoods and the Local Economy. | Strengthen local service nodes. | LED | Local community | 7-years | [25 empty] | 8000000 | 1500000 | Municipality/ EDTEA/ COGTA | 2026: Sourcing of funds | 3 | Buy-in from farmers/traders. Town planning restrictions in terms of Planning By-Laws on the location and establishment of rural markets. | Engagements with informal traders on needs and locations. Engagement with Spatial Planning to identify locational/land development requirements in relation to stalls etc. | Nil | NA
LED-03 | Develop an Agricultural Innovation and Market Feasibility Study. | Undertake a technical and market feasibility study to identify climate-resilient crops, niche agricultural opportunities, value chains, and pilot project locations, including implementation recommendations. | All TCs | Underdeveloped agricultural value chains and limited market access. | Support Agriculture as Food Security and Resilience Function. | Support small-scale and subsistence agriculture. | LED | Local community | 2-years | [25 empty] | 6000000 | 1000000 | DLRRD | 2026: Sourcing of funds | 3 | Availability of budget. Sector Department support. | Link study to pilot projects. Work through local cooperatives. | Nil | NA
LED-04 | Expansion of proven agricultural and rural market initiatives - that have demonstrated viability during the medium term. | Expand successful agricultural and rural market pilot projects into additional settlement areas, including infrastructure, training, storage, and logistics support based on proven models. | All TCs | Need to strengthen sustainable household income. | Strengthen Livelihoods and the Local Economy. | Strengthen local service nodes and livelihoods. | LED | Local community | 10-years | [25 empty] | 15000000 | 3000000 | Municipality/ EDTEA/ COGTA | 2026: Sourcing of funds | 3 | Results of medium-term pilots performance. Sector support. | Scale only proven pilots. Focus on TCs with strongest supporting conditions. | Nil | NA
LED-05 | Tourism Route Road Upgrades (P477, P556, AE3611, P26, L823, P21-1) | Upgrading of strategic tourism and eco-adventure routes linking rural attractions and scenic corridors. Gravel to tar upgrades (where feasible), Drainage improvements, Road safety signage, Wayfinding and tourism markers | P477, P556, AE3611, P26, L823, P21-1 | Poor accessibility; underdeveloped eco-tourism network; limited visitor movement between nodes. | Strengthen rural tourism corridors and increase inter-node connectivity. | Develop scenic route circuits linking agricultural, cultural and adventure tourism assets. | Transport and tourism-support infrastructure | Tourism operators; local businesses; rural communities. | 5–10 years (phased) | [25 empty] | 15000000 | 5000000 | MIG | 2026: Sourcing of funds | 3 | Funding uncertainty; high capital cost. | PPP structuring; phased upgrades; integration into provincial plans. | Road reserve approvals; environmental screening. | 2027
LED-06 | Nhlazanyoni Agro-Processing Rural Market | Establish a small-scale agro-processing and rural market facility supporting livestock, vegetable and dairy cooperatives. Basic agro-processing equipment (cold storage, packaging, grading area). Small abattoir / dairy handling section (subject to compliance). Storage facility | Nhlazanyoni | Limited rural agro-processing infrastructure; lack of formal market access for smallholder farmers; value chain leakage to urban centres. | Strengthen Nhlazanyoni as a functional rural service node supporting agricultural production and localised value addition. | Promote decentralised agro-processing linked to rural production zones; reduce transport costs to urban markets; support cooperative-based enterprise development. | LED | Smallholder farmers; livestock cooperatives; informal traders; rural households; youth and women enterprises. | 4 years (planning to full operation) | [25 empty] | 8000000 | 2000000 | DARD; COGTA; MIG; Agri-SETA partnerships | 2026: Sourcing of funds | 2 | Limited cooperative capacity; compliance approvals; operational sustainability risks. | Capacity building through DARD; phased implementation; private operator partnerships; early compliance approvals. | Rezoning; Site Development Plan approval; Environmental Authorisation (if triggered); Building plan approval. | 2027
LED-07 | Table Mountain-Maqongqo Cultural & Heritage Tourism Precinct | Develop a tourism node integrating heritage, cultural and eco-based activities along the scenic P26 corridor. Visitor information centre, craft market stalls, cultural exhibition space, wayfinding signage | Maqongqo | Untapped rural tourism economy; lack of structured tourism infrastructure; low visitor spend retention. | Establish Maqongqo as a recognised cultural tourism node within the rural tourism network. | Develop tourism clusters along scenic routes; formalise local craft economy; integrate eco-tourism and heritage assets | Tourism infrastructure and precinct development | Local artisans; tourism operators; youth enterprises; rural households. | 3–5 years | [25 empty] | 6000000 | 1500000 | EDTEA; COGTA; Tourism Incentive Programme | 2026: Sourcing of funds | 2 | Low visitor volumes; maintenance neglect. | Low visitor volumes; maintenance neglect. | None | N/A
LED-08 | ICT Access Points | Develop digital access and training centres to empower rural youth with digital and entrepreneurial skills. | Nhlazanyoni, Nkanyezini, Nonzila, eNtsongeni, KwaDwengu | Limited ICT access; digital exclusion; youth unemployment. | Reduce digital divide across rural settlement nodes. | Decentralise digital infrastructure to rural nodes; integrate ICT hubs into community facilities. | LED | Youth; job seekers; SMMEs; learners. | 3-years | [25 empty] | R3 500 000,00 per facility | 1000000 | SEDA; DSBD; Private ICT partnerships | 2026: Sourcing of funds | 2 | Operational sustainability; vandalism; low uptake. | School partnerships; community ownership models; security installation. | No change of required as ICT Access Points are to be co-located with existing social facilities | N/A
LED-09 | Community Furniture & Block Manufacturing | Establish small-scale manufacturing cooperatives in Camperdown/ Eston for furniture and concrete block production. | Camperdown/ Eston | Limited local manufacturing; dependency on external suppliers; low industrial diversification. | Strengthen local production capacity within primary and secondary nodes. | Promote light industrial activities linked to corridor markets; support cooperative-based enterprises. | LED | Local cooperatives; unemployed youth; small contractors. | 3-years | [25 empty] | 7000000 | 2000000 | DSBD / COGTA | 2026: Sourcing of funds | 3 | Market access constraints; cooperative management challenges. | Business mentorship; supply agreements with local projects. | Land use confirmation; building plan approval. | 2026
LED-10 | Corridor Micro-Logistics | Develop small-scale transport and logistics support services along R603 and P556 corridors. Loading bays, storage depots, informal trader support shelters | R603 and P556 Corridors | Weak linkages between production areas and markets; high transport costs; fragmented rural logistics. | Strengthen corridor-linked rural economic integration. | Develop logistics support nodes along strategic routes; integrate rural producers into broader supply chains. | LED | Farmers; cooperatives; small traders; transport operators. | 4-6years | [25 empty] | 5000000 | 1500000 | COGTA / DoT | 2026: Sourcing of funds | 3 | Land availability; coordination with transport authorities. | Early land assembly; intergovernmental coordination. | Land use confirmation; building plan approval. | 2026
LED-11 | ICT Access Points | Develop digital access and training centres to empower rural youth with digital and entrepreneurial skills. | Camperdown, Mpangasa, eSogweni, Milterton, Umkomazi, Manderston | Limited ICT access; youth unemployment; digital exclusion in rural settlements. | Close digital access gaps across all municipal wards. | Distribute ICT hubs across rural settlement hierarchy to ensure equitable access. | LED | Youth; SMMEs; learners; job seekers. | 3-years | [25 empty] | R3 500 000,00 per facility | 1000000 | SEDA / DSBD | 2026: Sourcing of funds | 2 | Operational sustainability; vandalism; equipment obsolescence. | Security installations; partnerships with schools; structured maintenance planning. | No change of required as ICT Access Points are to be co-located with existing social facilities | N/A
SF-01 | Construction of an Early Childhood Development centre. | Construct a basic ECD facility in a priority settlement cluster, including classrooms, ablutions, secure play areas, and water and electricity connections, in accordance with provincial ECD norms. | Manyavu | Limited access to early childhood facilities. | Improve Access to Social Facilities and Community Infrastructure. | Identify priority locations for education and ECD facilities. | Community Services | Local Community | 5-years | [25 empty] | 2250000 | 1500000 | Department of Education | 2026: Sourcing of funds | 3 | Availability of budget. Meeting threshold requirements for an ECD Centre. Land availability. | Engagement with Department of Education on proposal and possible alternatives utilising existing buildings/centres. | SPLUMA | 2027
SF-02 | Construction of an Early Childhood Development centre. | Construct a basic ECD facility in a priority settlement cluster, including classrooms, ablutions, secure play areas, and water and electricity connections, in accordance with provincial ECD norms. | Embo-Thimuni | Limited access to early childhood facilities. | Improve access to social facilities and community infrastructure. | Identify priority locations for education and early childhood facilities in densifying settlements. | Community Services | Local Community | 5-years | [25 empty] | 2250000 | 1500000 | Department of Education | 2026: Sourcing of funds | 3 | Availability of budget. Meeting threshold requirements for an ECD Centre. Land availability. | Engagement with Department of Education on proposal and possible alternatives utilising existing buildings/centres. | SPLUMA | 2027
SF-03 | Upgrade and expansion of existing clinic facilities. | Upgrade and expand existing clinic structures to increase capacity, including additional consultation rooms, waiting areas, ablutions, and improved water, sanitation, and electricity services. | Isimahla | Limited access to primary healthcare services. | Improve Access to Social Facilities and Community Infrastructure. | Identify priority locations for social facilities. | Community Services | Local Community | 5-years | [25 empty] | 15000000 | 2500000 | Department of Health | 2026: Sourcing of funds | 1 | Availability of budget. Department of Health approval - staffing allocation. | Focus on expansion of existing clinics. Align with health infrastructure plans. Phased implmentation and multi-year budgeting. | Nil | NA
SF-04 | Upgrade of existing community halls into multi-purpose service centres (ECD space, resource rooms, ICT, docking points for mobile clinics, SASSA and other outreach services). | Upgrade of existing community halls into multi-purpose service centres (ECD space, resource rooms, ICT, docking points for mobile clinics, SASSA and other outreach services). | All TCs | Limited access to social services due to distance and dispersed settlements. | Improve Access to Social Facilities and Community Infrastructure. | Promote multi-purpose and shared facilities. | Community Services | Local Community | 7-years | [25 empty] | 18000000 | 5000000 | Municipality/ Sector Departments | 2026: Sourcing of funds | 2 | Availability of budget. Detailed risks and/or dependencies to be confirmed during feasibility/design phases - in terms of services to be provided. Agreement with Traditional Councils. | Upgrade halls already in active use. Establish local management committees. Phased implmentation and multi-year budgeting. | To be confirmed during feasibility/design phase | 2026
SF-05 | Thusong Service Centre | Establishment of a multi-service Thusong Centre to centralise access to government services within the primary municipal node. | Camperdown | Fragmented service delivery and long travel distances for rural residents | Consolidate higher-order social services in the primary node | Node-based service concentration to improve efficiency and reduce duplication | Community Services | Local Community | 5 | [25 empty] | 22000000 | 6000000 | COGTA / DPSA | 2026: Sourcing of funds | 2 | Underutilisation if departmental commitments are not secured | Formal intergovernmental agreements before construction | Site development plan; building plan approval | 2026
SF-06 | District Hospital Feasibility & Site Acquisition | Feasibility study and land acquisition for future Level 1 District Hospital. | Municipal-wide strategic site (likely Camperdown influence area) | Absence of district-level hospital facility within municipality | Provide accessible secondary healthcare services within municipal boundaries | Strategic health infrastructure located along primary movement corridor | Community Services | Local Community | 12-years | [25 empty] | 60000000 | 10000000 | DoH/ UMDM | 2026: Sourcing of funds | 3 | Provincial funding dependency | Align with Provincial Health Infrastructure Plan early. | Land acquisition; SPLUMA approval; environmental screening. | 2027
SF-07 | Mpangisa Primary Clinic | Construction of a new primary healthcare clinic | Mpangisa | Clinic backlogs and long travel distances to nearest primary facility | Strengthen decentralised primary healthcare access | Provide lower-order clinics within rural clusters | Community Services | Local Community | 8-years | [25 empty] | 25000000 | 5000000 | DoH/ UMDM | 2026: Sourcing of funds | 3 | Provincial funding dependency | Align with Provincial Health Infrastructure Plan early. | Land acquisition; SPLUMA approval; environmental screening. | 2027
SF-08 | Disaster Management Centre (Camperdown) | Construction of a fully equipped disaster management centre | Camperdown | Limited local disaster response coordination capacity | Improve municipal disaster preparedness and response | Centralise emergency coordination within primary node | Community Services | Local Community | 8-years | [25 empty] | 25000000 | 5000000 | DoH/ UMDM | 2026: Sourcing of funds | 3 | Provincial funding dependency | Align with Provincial Health Infrastructure Plan early. | Land acquisition; SPLUMA approval; environmental screening. | 2027
SF-09 | Umkomazi Primary Clinic | Construction of a new primary healthcare clinic | Umkomazi | Clinic backlogs and long travel distances to nearest primary facility | Strengthen decentralised primary healthcare access | Provide lower-order clinics within rural clusters | Community Services | Local Community | 8-years | [25 empty] | 25000000 | 5000000 | DoH/ UMDM | 2026: Sourcing of funds | 3 | Provincial funding dependency | Align with Provincial Health Infrastructure Plan early. | Land acquisition; SPLUMA approval; environmental screening. | 2028
SF-10 | Regional Cemetery Facility & Phase 1 Build | Undertake feasibility and environmental assessment for new regional cemetery; acquire and service 8–10ha site for phased roll out. | Municipal-wide assessment for a strategic site | Existing and projected cemetery backlogs | Provide sustainable burial capacity over 20-year horizon | Consolidate regional cemetery capacity with phased expansion | Community Services | Local Community | 5-years | [25 empty] | 15000000 | 4000000 | COGTA / DPWI | 2026: Sourcing of funds | 3 | Community resistance to site location | Traditional leadership consultation prior to land confirmation | Land acquisition; rezoning; environmental screening. | 2026
SF-11 | Mpangisa Secondary School | Construction of a new secondary school to address backlogs in senior phase education facilities | Mpangisa | Existing secondary education backlog and overcrowding | Provide equitable access to secondary education within rural clusters | Locate secondary education facilities in high-demand rural service nodes to reduce learner travel distances | Community Services | Local Community | 5-years | [25 empty] | 35000000 | 8000000 | DoE | 2026: Sourcing of funds | 2 | Provincial budget constraints delaying implementation | Align project with Provincial Education Infrastructure Master Plan | Land acquisition/confirmation; environmental screening; building plan approval. | 2026
SF-12 | Mpandwini Secondary School | Construction of a new secondary school to address backlogs in senior phase education facilities | Mpandwini | Existing secondary education backlog and overcrowding | Provide equitable access to secondary education within rural clusters | Locate secondary education facilities in high-demand rural service nodes to reduce learner travel distances | Community Services | Local Community | 5-years | [25 empty] | 35000000 | 8000000 | DoE | 2026: Sourcing of funds | 2 | Provincial budget constraints delaying implementation | Align project with Provincial Education Infrastructure Master Plan | Land acquisition/confirmation; environmental screening; building plan approval. | 2029
SF-13 | Mid-Illovo Primary Clinic | Construction of a new primary healthcare clinic | Mid-Illovo | Clinic backlogs and long travel distances to nearest primary facility | Strengthen decentralised primary healthcare access | Provide lower-order clinics within rural clusters | Community Services | Local Community | 8-years | [25 empty] | 25000000 | 5000000 | DoH/ UMDM | 2026: Sourcing of funds | 3 | Provincial funding dependency | Align with Provincial Health Infrastructure Plan early. | Land acquisition; SPLUMA approval; environmental screening. | 2032
SF-14 | Manderston Primary Clinic | Construction of a new primary healthcare clinic | Manderston | Clinic backlogs and long travel distances to nearest primary facility | Strengthen decentralised primary healthcare access | Provide lower-order clinics within rural clusters | Community Services | Local Community | 8-years | [25 empty] | 25000000 | 5000000 | DoH/ UMDM | 2026: Sourcing of funds | 3 | Provincial funding dependency | Align with Provincial Health Infrastructure Plan early. | Land acquisition; SPLUMA approval; environmental screening. | 2027
SF-15 | Mpandwini Primary Clinic | Construction of a new primary healthcare clinic | Mpandwini | Clinic backlogs and long travel distances to nearest primary facility | Strengthen decentralised primary healthcare access | Provide lower-order clinics within rural clusters | Community Services | Local Community | 8-years | [28 empty] | 2026: Sourcing of funds |  |  |  |  | 2032
SF-16 | Milterton Primary Clinic | Construction of a new primary healthcare clinic | Milterton | Clinic backlogs and long travel distances to nearest primary facility | Strengthen decentralised primary healthcare access | Provide lower-order clinics within rural clusters | Community Services | Local Community | 8-years | [28 empty] | 2026: Sourcing of funds
ENV-01 | Implementation of long-term erosion control and settlement protection programs. | Implement large-scale slope stabilisation, gully rehabilitation, vegetative restoration, and protective earthworks in high-risk settlement areas identified through environmental and hazard mapping. | Embo-Thimuni and Maphumulo | Ongoing exposure of settlements to erosion and flooding. | Build Long-Term Community Resilience. | Reduce exposure to environmental and service-related risks. | Disaster Management/ Environment | Local communities | 7-years | [25 empty] | 18000000 | 4000000 | Municipality/ EDTEA/ COGTA | 2026: Sourcing of funds | 2 | Availability of budget. | Phased implmentation and multi-year budgeting. Align with Sector Plans. | Nil | NA
ENV-02 | Implementation of climate adaptation measures aligned with sector plans and disaster risk frameworks. | Implement climate adaptation interventions aligned with sector plans, including drought mitigation measures, flood protection works, water conservation systems, and heat-resilient community infrastructure | All TCs | Increasing climate change impacts on livelihoods and infrastructure. | Build Long-Term Community Resilience. | Integrate resilience considerations into planning. | Disaster Management/ Environment | Local communities | 10-years | [25 empty] | 12000000 | 3000000 | Municipality/ EDTEA/ COGTA | 2026: Sourcing of funds | 2 | Availability of budget. Alignment with Sector Plans. Alignment with Disaster Management programs. | Phased implementation and multi-year budgeting. Integrate into existing infrastructure projects. Align with Sector Plans. | Nil | NA
ENV-03 | Relocation of households in steep slopes | Identification and relocation of households located within river buffers, floodplains and steep slopes to safer, planned residential areas. | Mdaphuma, Table Valley, Islay, Ukhalo, Villa Maria, Table Mountain, Nonzila | Flood risk, slope instability, riverbank erosion and environmental non-compliance. | Restructure settlement patterns away from environmentally hazardous areas | Enforce environmental buffers and consolidate growth within suitable land parcels | Disaster Management/ Environment | Local communities | 15-years | [25 empty] | 70000000 | 5000000 | DoHS | 2026: Sourcing of funds | 3 | Land availability and community resistance | Early public participation and phased relocation with serviced land prepared beforehand | SPLUMA approvals | 2026
ENV-04 | River & Wetland Rehabilitation | Rehabilitation of riverbanks, wetlands and riparian buffers through vegetative planting, sediment control, invasive species removal and erosion stabilisation. 30m vegetative buffers, gabions & sediment traps, invasive alien clearing, river clean-up campaigns, stormwater flow control | Lowu River, uMbango River, Mkhomazi River, Islay River, Mpangisa, eQqweni, Camperdown, Millerton | Riverbank erosion, sedimentation, pollution and biodiversity loss | Restore ecological corridors and reduce flood vulnerability | Embed green infrastructure into municipal stormwater and land use management | Disaster Management/ Environment | Local communities | 8-years | [25 empty] | 8000000 | 1000000 | DWS / EDTEA / EPWP | 2026: Sourcing of funds | 1 | Lack of maintenance leading to recurrence of degradation | Community-based EPWP maintenance model | None | N/A
ENV-05 | School Rainwater Harvesting | Installation of rainwater harvesting systems at schools to address water scarcity and support sanitation | EmaZwini High School; Milterton Primary School; Gina Primary School; iMboyi Primary School | Water scarcity during dry periods, limiting sanitation functionality, hygiene outcomes and food garden initiatives at schools | Improve resilience of social infrastructure (schools) in rural clusters and reduce vulnerability to water supply disruptions | Support decentralised, low-cost water resilience interventions at community facilities located in rural nodes where supply interruptions are more frequent | Disaster Management/ Environment | Local communities | 3-years | [25 empty] | 1000000 | 300000 | DoE/ DWS | 2026: Sourcing of funds | 1 | School site readiness and maintenance capacity constraints may result in poor upkeep, leakages or non-functioning systems over time | Include caretaker training, simple O&M schedules, and annual inspection tied to school maintenance planning, with secure installation to prevent theft/vandalism. | None | N/A
ENV-06 | Forest & Biodiversity Restoration | Implementation of forest rehabilitation, conservation and community afforestation initiatives to restore degraded ecosystems, reduce erosion and improve biodiversity integrity in priority areas. | Ngilanyoni; Entsengeni; KwaDwengu | Deforestation, forest fragmentation, loss of biodiversity and soil degradation; encroachment and logging pressures in some areas | Protect and restore ecological assets that function as environmental support systems and buffers against climate and erosion impacts | Strengthen ecological corridors and indigenous vegetation systems through targeted restoration, community-based conservation and long-term stewardship. | Disaster Management/ Environment | Local communities | 3-years | [25 empty] | 8000000 | 2000000 | DFFE | 2026: Sourcing of funds | 1 | Low seedling survival due to drought, grazing pressure, fires, or continued encroachment and illegal harvesting. | Use drought-resistant indigenous species, protect sites through community stewardship and demarcation, integrate fire management measures, and include follow-up replanting and invasive control in the programme budget | None | N/A
DIS-01 | Installation of lightening conductors | Installation of lightning conductors on public facilities and high-risk structures across multiple wards to reduce lightning-related fatalities, infrastructure damage and service disruption. | Ward 1, 2, 4, 6 and 7 | High incidence of lightning strikes causing fatalities, structural damage and disruption to public facilities | Improve municipal disaster resilience and reduce vulnerability of rural communities to lightning-related hazards | Implement preventative disaster mitigation measures across high-risk public facilities within rural and peri-urban settlements | Disaster Management | Local communities | 3-years | [25 empty] | 500000 | 150000 | COGTA | 2026: Sourcing of funds | 2 | Improper installation or lack of periodic maintenance may render systems ineffective | Use certified installers and implement scheduled inspection and compliance testing programme | None | N/A
DIS-02 | Provision of water harvesting tanks (JOJO tanks) | Provision and installation of 100 (5,000–10,000L water harvesting tanks) across all wards to strengthen water security during drought and disaster events. | All Wards | Drought vulnerability and unreliable water access during disaster periods | Improve household-level resilience to water supply disruption | Introduce decentralised water resilience measures in high-risk rural clusters | Disaster Management | Local communities | 3-years | [25 empty] | 1500000 | 400000 | MLM/ COGTA | 2026: Sourcing of funds | 1 | Poor maintenance leading to non-functionality | Community awareness and annual inspection schedule | None | N/A
DIS-03 | Planting of trees to minimise wind speed | Strategic planting of wind-resistant tree buffers in strong wind-prone areas | All Wards | Strong winds causing structural damage and safety risks | Reduce settlement vulnerability to extreme weather | Integrate green infrastructure into settlement risk reduction | Disaster Management | Local communities | 3-years | [25 empty] | 1000000 | 250000 | MLM/ COGTA | 2026: Sourcing of funds | 1 | Tree mortality due to lack of maintenance | Maintenance contract for first 24 months and community stewardship | None | N/A
DIS-04 | Installation of road traffic signs | Installation of road traffic signs in high MVA-risk areas. Warning signs, speed control signage, reflective road markers, basic traffic calming measures | All Wards | High motor vehicle accident rates in specific corridors | Improve road safety and reduce accident-related disaster response | Targeted infrastructure intervention at identified high-risk zones | Disaster Management | Local communities | 3-years | [25 empty] | 500000 | 150000 | MLM/ COGTA | 2026: Sourcing of funds | 1 | Vandalism or theft of signage | Secure installation and routine monitoring | None | N/A
DIS-05 | Installation of fire Hydrants | Installation of fire hydrants across priority wards and implementation of continuous fire break programme in structural and veld fire-prone areas. | Wards 1, 3, 4, 6 | Fire risk in dense settlements and veld areas | Reduce fire-related disaster loss and response times | Combine structural fire suppression infrastructure with preventative land management | Disaster Management | Local communities | 3-years | [25 empty] | R50,000 annually | R1 000 000,00 (combined) | UMDM / MLM / COGTA | 2026: Sourcing of funds | 1 | Lack of water pressure rendering hydrants ineffective | Coordinate hydrant installation with bulk water pressure verification | None | N/A