## MKHAMBATHINI CIF
PROJECT NO. | PROJECT NAME/ DESCRIPTION | PROPOSED SPECIFICATIONS | LOCATION | CHALLENGE TO BE ADDRESSED/ KEY ISSUE | LONG-TERM SPATIAL OBJECTIVE | LONG-TERM SPATIAL STRATEGY | TYPE OF PROGRAM/ PROJECT | BENEFICIARIES OF INTERVENTION | ESTIMATED DURATION OF PROJECT | ESTIMATED START AND END DATES | [9 empty] | FUNDS |  |  | PROJECT STATUS | PRIORITY LEVEL (1-5) | PERCIEVED RISKS TO IMPLEMENTATION/ DEPENDENCIES ON OTHER PROJECTS | MEANS OF MITIGATING PERCIEVED RISKS | APPLICABLE LAND DEVELOPMENT PROCEDURES AND/OR APPLICATIONS | ESTIMATED DATE BY WHEN THE PROCEDURE OR APPLICATION NEEDS TO BE INITIATED
[10 empty] | CURRENT IDP TERM |  |  |  |  | 5 YEARS |  |  |  |  | ESTIMATED BUDGET | ESTIMATED COST OF MAINTAINANCE OVER 10 YEARS | PROPOSED SOURCE OF FUNDING
[10 empty] | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
ENV-01 | Alien species programme | Implementation of an alien invasive plant removal programme across all wards to protect biodiversity and strengthen climate resilience. Clearing of invasive alien vegetation, rehabilitation of cleared areas, manual and mechanical removal methods, training and equipping of EPWP participants | All 7 Wards | Proliferation of invasive alien species; reduced water security; biodiversity loss. | Protect ecological corridors and enhance environmental sustainability | Prioritise river systems and ecological networks; integrate alien clearing with disaster risk reduction and water conservation planning. | Environmental management and climate resilience programme (EPWP) | Local EPWP participants (±140); farmers; downstream water users; rural communities. | Ongoing (annual cycles) | [10 empty] | TBD | TBD | EPWP allocation (annual operational budget) | Planned | 2 | Re-infestation; limited long-term maintenance funding; seasonal labour dependency. | Phased clearing plan; community education; integration with agricultural extension programmes. | None | N/A
ENV-02 | Recycling and Environmental Education Programme | Diversion of recyclable waste from landfill through community education and waste separation initiatives, creating small-scale economic opportunities. | All 7 Wards | Low recycling rates; landfill pressure; limited waste-based economic activity. | Promote circular economy practices within rural settlements. | Develop decentralised recycling points; link recycling initiatives to SMME development and poverty alleviation. | Environmental management and economic empowerment | EPWP participants (±44); schools; informal waste collectors; SMMEs. | Ongoing (annual cycles) | [10 empty] | TBD | TBD | EPWP; Municipal waste budget; Private recycling partnerships | Planned | 2 | Market fluctuations for recyclables; low community participation. | Partnerships with recycling companies; sustained awareness campaigns. | None | 2026
ENV-03 | Waste Management and Litter Control Programme | Ward-based litter picking, illegal dumping removal and street cleansing programme to improve environmental health. | Wards 1, 2, 4, 5, 6 and 7 | Illegal dumping; environmental degradation; public health risks. | Maintain clean and functional settlement environments. | Prioritise high-density settlements and transport corridors; integrate waste enforcement and education. | Operational environmental service | EPWP participants (±49); residents; businesses; schools. | Ongoing (annual cycles) | [10 empty] | TBD | TBD | Municipal operational budget; EPWP | Planned | 3 | Recurring dumping; insufficient enforcement. | By-law enforcement; community awareness; hotspot monitoring. | None | N/A
ENV-04 | Open Space Management and Ecological Maintenance | Management and maintenance of public open spaces including grass cutting, stormwater drain cleaning, greening and conservation. | Wards 1, 2, 4, 5, 6 and 8 | Unmaintained open spaces; stormwater blockages; increased flooding and fire risk | Strengthen settlement resilience and environmental aesthetics. | Integrate open space management with disaster risk reduction and stormwater management systems. | Environmental and disaster risk mitigation/ management | EPWP participants (±26); residents; property owners. | Ongoing (annual cycles) | [10 empty] | TBD | TBD | Operational municipal and EPWP funding. | Planned | 2 | Budget constraints | Phased maintenance scheduling | None | N/A
ENV-05 | Town Beautification Programme | Targeted beautification and greening initiative within Ward 3 to improve visual quality and civic identity. | Ward 3 | Declining town aesthetics; reduced investor appeal. | Enhance town attractiveness and support small business activity. | Strengthen primary settlement node; improve investor perception. | Urban management | EPWP participants (±20); local businesses; residents | 2-years | [10 empty] | TBD | TBD | Municipal operational budget; EPWP | Planned | 2 | Short-term impact without sustained maintenance. | Integrated urban management plan; routine maintenance schedule. | None | N/A
ENV-06 | EDTEA Invasive Alien Plant Species | Large-scale invasive alien plant clearing programme implemented across all wards to strengthen biodiversity protection and climate resilience. | All Wards | Severe alien plant infestation; reduced water yield; increased veld fire risk; biodiversity degradation. | Protect and restore ecological infrastructure supporting water security, agriculture and climate adaptation. | Prioritise river catchments and environmentally sensitive areas; align alien clearing with municipal disaster risk reduction strategy. | Environmental restoration and climate mitigation | Local participants (±300); farming sector; downstream water users; rural communities. | 3–5 years (phased clearing cycles) | [10 empty] | TBD | TBD | EDTEA | Planned | 2 | Re-infestation; dependency on external funding cycles; limited post-clearing maintenanc | Integrate with municipal environmental programme; community awareness; phased follow-up clearing. | None | N/A
DIS-01 | Disaster Relief Support Programme | Provision of emergency relief support and response coordination across all wards. Emergency relief stock (food, blankets, temporary shelter); Basic response equipment | All Wards | High vulnerability to floods, lightning, storms and veld fires; limited immediate response capacity. | Strengthen rapid response and reduce post-disaster vulnerability. | Develop ward-based emergency response capacity; integrate with community structures. | Disaster response support programme | Vulnerable households; disaster-affected communities | Ongoing (annual cycles) | [10 empty] | 350000 | R350 000,00 Annual Allocation | Municipal disaster budget | Planned | 3 | Insufficient funding during major disaster events. | Provincial disaster funding applications; contingency planning. | None | N/A
DIS-02 | Lightning Conductors Installation Programme | Installation of lightning protection systems in high-risk public facilities and community structures. Proposed Specifications, Lightning conductors installed on schools and community halls, Earthing systems | All Wards | High lightning strike incidents; damage to infrastructure; risk to human life. | Reduce infrastructure damage and improve public safety. | Prioritise vulnerable rural wards; focus on schools and community facilities. | Disaster response support programme | Learners; community facility users. | 2-years | [10 empty] | 100000 | Minor inspection costs | Municipal disaster budget | Planned | 3 | Limited coverage due to budget constraints. | Phase installation; prioritise highest-risk facilities. | None | N/A
SF-01 | Imboyi Sport Field Development | Development of the Imboyi sport field to provide structured recreational infrastructure and community sports facilities. | Nkanyezini | Limited recreational infrastructure; youth vulnerability; underdeveloped community sport facilities. | Strengthen social infrastructure within rural settlements to support youth development and community cohesion. | Develop multi-purpose community facilities within rural nodes; integrate sport infrastructure into settlement development planning. | Community social infrastructure | Local communities | 1-2 years (construction and commissioning) | [10 empty] | TBD | TBD | Afrisam | Planned | 2 | Maintenance sustainability; vandalism; limited operational management. | Community sport committees; local caretaker appointment; partnership with schools; phased infrastructure upgrades.
SF-02 | Nobhala High School Classroom Construction | Construction of an additional classroom at Nobhala High School to improve learning conditions and accommodate growing enrolment. | Nobhala High School | Overcrowded classrooms; inadequate learning infrastructure; pressure on rural education facilities. | Strengthen educational infrastructure within rural settlements to improve human capital development. | Upgrade existing institutional nodes; prioritise social infrastructure in growth settlements. | Community social infrastructure | Local communities | 1-2 years (construction and commissioning) | [10 empty] | TBD | TBD | UMEDA (FSPSU & RASET) | Planned | 2 | Construction delays; alignment with Department of Education standards; long-term maintenance burden. | Early coordination with Department of Education; compliance with building norms and standards; maintenance planning in school budget. | Building plan approval | 2026
HSD-01 | Stockdale Integrated Settlement Upgrade (ISU) | Implementation of Stage 1 Integrated Settlement Upgrade (ISU) for Stockdale, including detailed planning, township establishment and servicing preparation (250 housing units); Township establishment; Internal roads and stormwater; Bulk service connections (water, sanitation, electricity); Site pegging and surveying | Ward 4 – Stockdale Settlement | Inadequate formal housing; incomplete township establishment; limited bulk infrastructure funding. | Formalise and consolidate Stockdale as a structured residential settlement. | Upgrade informal housing areas through phased township establishment; align with bulk service investment planning. | Human Settlements Project (ISU – Stage 1) | 250 beneficiary households; Ward 4 residents. | 6 years (Stage 1 implementation) | [10 empty] | R1 634 650 (Planning Stage) | N/A | KZN DHS; HDA; Municipal bulk infrastructure grant | Stage 1 – Planning advanced; SPLUMA approval pending; bulk funding required. | 4 | Delay in SPLUMA approval; bulk infrastructure funding shortfall; engineering approval delays. | Fast-track municipal planning approvals; coordinated engagement with DHS and HDA; phased bulk funding approach. | SPLUMA approval; General Plan approval; engineering services approval; township establishment; building plan approvals. | 2026 (Already underway)
HSD-02 | Mkhambathini Ward 2, 3 & 5 Rural Housing Project (RHP) | Large-scale Rural Housing Project delivering 2 000 housing units across Wards 2, 3 and 5; 2 000 housing units; Engineering services design and approvals; Geotechnical compliance; Settlement layout and social compact; Bulk service coordination | Wards 2, 3 and 5 (Dispersed rural settlements) | Rural housing backlog; inadequate serviced stands; dispersed settlement growth without structured planning. | Provide structured rural housing while aligning with nodal growth strategy. | Consolidate rural settlement clusters; integrate housing delivery with service investment and access planning. | Rural Human Settlements Project | 2 000 rural households | 8 years (Stage 1 implementation) | [10 empty] | R7 462 240 (Planning & preliminary stages) | N/A | KZN DHS; HDA; Municipal bulk infrastructure grant | Stage 1 commenced; planning advanced; engineering approval pending. | 4 | Bulk service constraints; engineering approvals; contractor performance risk. | Phased rollout; performance-based contractor monitoring; alignment with bulk service upgrades. | SPLUMA approvals; engineering services approval; environmental compliance (if triggered). | 2026 (Already underway)
HSD-03 | Camperdown Development Node (IRDP) | Integrated Residential Development Programme (IRDP) at Camperdown Development Node delivering 9 000 housing opportunities; 9 000 residential units (phased); Full township establishment; Bulk water and sanitation infrastructure; Internal road network; Social facilities provision (schools, clinics, open space); Mixed-income typologies (subject to DHS approval) | Ward 3 – Camperdown Primary Node | Large housing backlog; underdeveloped primary node; need for structured urban growth corridor along N3 influence zone. | Establish Camperdown as a primary urban node supporting mixed-use growth and corridor-linked development. | Concentrate large-scale housing within primary node; integrate with transport corridors; align with bulk infrastructure expansion. | Human Settlements Settlement Development (IRDP) | 9 000 beneficiary households; emerging middle-income groups; local construction sector | 10–15 years (multi-phase mega project) | [10 empty] | R76 329 000,00 (Approved Funding Planning) | N/A | KZN DHS; SCM process; possible bulk co-funding (COGTA / MIG) | Contract signed; awaiting inception from Mkhambathini LM. | 4 | Bulk wastewater capacity constraints; land readiness; intergovernmental coordination delays. | Align with bulk WWTW upgrade project; establish dedicated project steering committee; phased service delivery. | Township establishment; SPLUMA approval; Environmental Authorisation; General Plan approval; engineering services approval; building plan approval. | 2026
HSD-04 | uMgungundlovu – Verification of People with Disabilities | Verification and profiling of beneficiaries with disabilities within the uMgungundlovu housing programme to ensure compliant and inclusive housing delivery; Beneficiary verification audit (±2000 beneficiaries); Needs assessment for accessible housing typologies; Alignment with Human Settlements beneficiary database; Development Programme refinement | All wards | Incomplete beneficiary profiling; risk of non-compliant housing typologies; delays in drafting detailed Development Programme. | Ensure inclusive human settlement delivery aligned to universal access standards. | Integrate disability-responsive housing design within IRDP, RHP and UISP projects; strengthen beneficiary database accuracy. | Human Settlements Planning and Beneficiary Verification (Pre-Implementation Enabler) | ±2000 registered housing beneficiaries; persons with disabilities. | 12–18 months | [10 empty] | TBC | N/A | KZN DHS | Pre-feasibility (Project Manager newly appointed) | 3 | Data inaccuracies; delays in Development Programme drafting. | Dedicated project management oversight; alignment with DHS beneficiary systems. | None (Planning and verification process). | N/A
HSD-05 | uMgungundlovu UISP (ISUPG) – Informal Settlement Upgrading Programme | Implementation of the Upgrading of Informal Settlements Programme (UISP) across identified informal settlements in Ward 3. Settlement planning and layout formalisation; Engineering services planning; Geotechnical investigations; Community participation structures (PSC formation); Incremental upgrading and basic service installation | Ward 3: Emabhodini (B1); Farm Mist (KwaMadolo) (B2); KwaMavindelani (B2); Mandaleni (B1); Sotobe; Umlaas Road IS (C); Umlaas Road IS 2 (C) | High informal settlement density (±1234 households); insecure tenure; limited services; funding discontinuity. | Incrementally formalise informal settlements and integrate them into structured settlement framework. | Prioritise B1 and B2 settlements for upgrading; consolidate C-category settlements through phased reconfiguration; align with bulk infrastructure planning. | Human Settlements Programme (UISP – Incremental Upgrading) | ±1234 households; informal settlement residents in Ward 3. | 5-10 years | [10 empty] | TBC | TBC | KZN DHS | Service Provider appointed; work halted pending approved budget for new financial year. | 4 | Budget approval delays; community participation disruption; bulk service constraints. | Fast-track budget approval; re-engage PSC structures; align with bulk infrastructure upgrades. | Layout approval; Environmental screening; Engineering services approval; SPLUMA compliance (where triggered); land tenure regularisation. | 2026
HSD-06 | Mkhambathini Ward 7 Rural Housing Project | Phased Rural Housing Project delivering 300 housing units in Ward 7, including slab, wall plate, roofing and completion stages; 300 rural housing units; On-site service provision (as per rural standards); Conversion of roofed units to full completions; Incremental construction model | Ward 7 | Housing backlog; construction delays due to social issues, inclement weather and budget cuts; difficult terrain impacting progress. | Reduce rural housing backlog while consolidating structured rural settlement clusters. | Phase rural housing delivery in manageable construction blocks; align delivery with terrain and accessibility conditions; prioritise completion of partially built units. | Rural Human Settlements Project | 300 rural beneficiary households. | 7 years | [10 empty] | R58 016 269.66 | TBC | KZN DHS | Phase 1 completed (500 units); Phase 2 underway; Implementing Agent on site; end date July 2026. | 4 | Terrain constraints; contractor capacity; budget adjustments. | Deployment of additional construction teams; terrain-sensitive construction sequencing; strict contractor performance monitoring. | SPLUMA approvals; environmental compliance; beneficiary verification. | 2026 (Already underway)
HSD-07 | KwaMahleka Rural Housing Project | Rural housing project delivering approximately 500 housing units in Ward 4; 500 rural housing units; Slab to completion construction model; Realignment of subsidy quantum; Appointment of new implementing agent | Ward 4 | Project delays; contractor underperformance; implementing agent liquidation; stalled construction; subsidy realignment required. | Complete stalled rural housing project and restore delivery credibility. | Stabilise project management; reappoint capable service provider; fast-track completions of partially built units. | Rural Human Settlements Project | 500 rural households. | 10 years | [10 empty] | R51 817 463.74 | TBC | KZN DHS | Contract not renewed; realignment approved (July 2025); new service provider appointment pending. | 4 | Procurement delays; further contractor failure; subsidy quantum misalignment. | Strict SCM oversight; performance-based contracts; project steering committee monitoring. | Existing approvals in place; contract reappointment via SCM; engineering compliance review. | 2026
HSD-08 | KwaNjobokazi Rural Housing Project | Rural housing development delivering 400 units in Ward 5 under phased construction; Slab-to-completion model; Subsidy quantum realignment (approved); Contractor performance stabilisation | Ward 5 | Implementing agent instability; business rescue proceedings; legal disputes; insufficient contractor presence on site; financial strain due to subsidy quantum limits. | Complete rural housing delivery and stabilise settlement growth. | Prioritise completion of partially constructed units; align revised subsidy quantum with realistic construction costs. | Rural Human Settlements Project | 400 rural households | 7 years | [10 empty] | R43 093 048.40 | TBC | KZN DHS | Subsidy realignment approved (24-month adjustment); construction ongoing with performance challenges. | 4 | Contractor underperformance; cost escalation; further legal disputes. | Tight contract supervision; milestone-based payment controls; contractor capacity assessment. | Existing rural housing approvals; compliance monitoring; contract management oversight. | N/A
HSD-09 | Maqongqo Rural Housing Project | Rural housing development delivering 500 units in Maqongqo under phased construction; Slab-to-completion construction model; Completion of partially built units (495 slabs; 454 completions achieved) | Ward 1 | Historical contractor non-performance; project realignment; transition to new implementing agent; finalisation of remaining units. | Complete rural housing delivery and stabilise Maqongqo settlement structure. | Prioritise completion of near-finished units; avoid prolonged capital exposure; consolidate settlement growth around serviced clusters. | Rural Human Settlements Project | 500 rural households (with 454 nearing completion stage). | 6 years | [10 empty] | R44 558 093.03 | TBC | KZN DHS | Implementing Agent surrendered; new contractor appointed; contract finalisation pending. | 4 | Further contractor transition delays; escalation of completion costs. | Fast-track contract finalisation; milestone-based payment control; strict quality assurance inspections. | Existing rural housing approvals; compliance verification; beneficiary confirmation. | 2026
HSD-10 | Mkhambathini 56 OSS (Rural) | Provision of 56 rural housing units under the OSS programme targeting vulnerable households; 56 housing units (59 units recorded due to emergency inclusions); Full construction and completion; Close-out documentation and final invoicing | Ward 2 and 5 | Delayed construction; finalisation of outstanding invoices; close-out administration. | Provide urgent housing support to vulnerable households. | Utilise OSS model for urgent rural interventions; integrate into broader rural housing rollout | OSS Human Settlements Project | 56 beneficiary households (including 3 urgent cases). | 4 years | [10 empty] | R11 896 562.00 | TBC | KZN DHS | All houses complete; close-out documentation in progress. | 4 | Delayed invoice processing; audit findings at close-out stage. | Expedite financial reconciliation; technical compliance verification prior to closure | None additional (construction complete) | N/A
HSD-11 | Mkhambathini 50 OSS Housing Project | Delivery of 50 OSS rural housing units for vulnerable families in Ward 5. 50 rural housing units; Slab, wall plate, roofing and completion stages; Recovery plan implementation; Contractor stabilisation | Ward 5 | Delayed commencement; contractor performance issues; financial constraints; project recovery implementation | Provide urgent housing to vulnerable families and stabilise rural settlement growth | Prioritise completion of partially built units; enforce contractor compliance; integrate OSS delivery with broader rural housing planning | OSS Human Settlements Project | 50 vulnerable households (Operation Sukuma Sakhe beneficiaries). | 4 years | [10 empty] | R8 830 924.50 | TBC | KZN DHS | Construction ongoing; contractor performance stabilised; monitored closely | 4 | Contractor underperformance; subsidy quantum limitations; financial strain | Strict on-site monitoring; milestone-based payments; contractor performance enforcement | Existing rural housing approvals; compliance verification | 2026
HSD-12 | uMgungundlovu Disaster Phase 1 | Construction of permanent houses for 2019 disaster-affected beneficiaries (17 units allocated to Mkhambathini). 17 permanent housing units; Slab, wall, roof and completion stages; Site access and terrain mitigation. | Various wards (Disaster-affected households) | Delayed construction due to terrain, weather, contractor capacity constraints and prior breach placement | Provide permanent housing to disaster-affected households and reduce temporary shelter reliance | Prioritise completion of outstanding disaster units; stabilise contractor performance; avoid multi-municipality contractor over-extension | Human Settlements Project | 17 disaster-affected households | 7 years | [10 empty] | R3 314 728.16 | TBC | KZN DHS | Construction ongoing; monitored closely | 4 | Service provider performance; financial constraints; access to remote sites | Milestone-based payment control; targeted site supervision; coordination with provincial DHS | Emergency housing approvals; compliance verification | 2026
HSD-13 | uMgungundlovu Disaster Phase 3 | Construction of 7 permanent housing units under the 2019 Disaster Programme (reallocated scope). 7 disaster housing units; Beneficiary administration; Contract finalisation and mobilisation | Various wards (Disaster-affected households) | Financial constraints; contractor transition; delayed commencement. | Complete reallocated disaster housing scope | Streamline contractor handover; align scope with available budget | Human Settlements Project | 7 disaster-affected households | 2 years | [10 empty] | R1 486 564.38 | TBC | KZN DHS | Service provider appointed; beneficiary administration commenced | 4 | Budget shortfall; delayed mobilisation | Fast-track contract signing; milestone-based monitoring | Emergency housing approvals; compliance verification | 2026
HSD-14 | uMgungundlovu Disaster Phase 4 | Construction of 30 permanent disaster housing units under Phase 4. 30 housing units; Full construction and completion; Contractor mobilisation (BVI Consultants) | Various wards (Disaster-affected households) | Budget constraints; contract drafting delays; reallocation from previous service provider | Conclude 2019 disaster housing programme backlog | Stabilise contractor transitions; prevent further scope reduction. | Human Settlements Project | 30 disaster-affected households | 4 years | [10 empty] | R6 237 006.60 | TBC | KZN DHS | Service provider appointment confirmed (July 2025); contract drafting underway | 4 | Budget constraints; contract delays; contractor capacity risk | Strict contract performance clauses; project steering oversight; phased construction scheduling | Emergency housing approvals; compliance verification | 2026
HSD-15 | Stockdale 260 Temporary Residential Units (TRUs) | Provision of 260 Temporary Residential Units (TRUs) in Stockdale to address court-ordered evictions; Interim services (water, sanitation, electricity); Site preparation and layout approval; Compliance with SPLUMA and MPT approval | Ward 3 | Court-ordered relocations; need for temporary accommodation; SPLUMA approval delays; interim service funding requirements. | Provide interim accommodation while transitioning beneficiaries into permanent housing solutions | Use TRUs as temporary relocation solution linked to permanent IRDP/ISU projects; avoid long-term informalisation of TRU settlements | Human Settlements Project | 260 displaced households | 2 years | [10 empty] | R23 848 070.00 | TBC | KZN DHS | SPLUMA presented to MPT; additional issues to be addressed; construction anticipated September 2026. | 4 | SPLUMA approval delays; interim service funding gaps; risk of TRUs becoming permanent informal structures | Fast-track land use approvals; strict temporary tenure framework; linkage to permanent housing pipeline | SPLUMA approval; MPT decision; site development plan; interim service approval | 2026
ID-01 | Bulk Wastewater Treatment Works Upgrade | Expansion and upgrading of bulk wastewater treatment capacity to support housing, industrial and commercial development. Increased treatment capacity; Reticulation upgrades; Effluent quality compliance systems; Bulk pipeline connections | Camperdown | Insufficient wastewater capacity; development constraints; environmental compliance pressures. | Enable structured urban expansion and industrial growth within designated nodes. | Align bulk services investment with nodal growth areas and corridor-linked development. | Bulk infrastructure development | Residents; developers; industries; commercial investors. | 10+ years: Current IDP: Feasibility and design (current IDP term); Infrastructure implementation (5 years); Capacity scaling with growth (10+ years) | [10 empty] | TBD | TBD | External (UMDM; Umgeni Water) | Planned / External | 4 | Funding gaps; environmental approvals; capacity mismatch. | Phased capacity expansion; alignment with SDF growth projections. | Environmental Authorisation; Water Use Licence; servitude registration. | 2027
ID-02 | Nkanyezini Reservoir | ±3 ML storage, Elevated tank, Bulk pipeline upgrade | Nkanyezini Rural Settlement Cluster | Water supply instability in rural settlements | Strengthen rural service nodes | Rural cluster service consolidation | Infrastructure development | Local communities | 3 years | [10 empty] | 35000000 | 6000000 | MIG | Planned | 4 | Bulk supply dependency | District-level integration | SPLUMA | 2026
ID-03 | P728 Bridge Upgrade | Reinforced concrete bridge; 8–10m carriage width; Stormwater resilience design | P728 | Poor access during floods | Improve agricultural logistics and emergency access | Strengthen rural movement network | Infrastructure development | Local communities | 3 years | [10 empty] | 20000000 | 6000000 | MIG | Planned | 4 | Hydrological complexity | Detailed geotechnical study | None | N/A
ID-04 | Upgrade of D977 (Concrete Surfacing) | 6–7m carriageway, concrete surfacing, drainage system | D977 | High maintenance due to heavy vehicles | Strengthen corridor support routes | Freight network reinforcement | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 4 | Funding availability | Phased delivery by highest-impact sections | None | N/A
ID-05 | Zinenbeni Access Road | Upgrade of Zinenbeni Access Road to improve internal settlement accessibility and all-weather access | Ward 1 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen internal settlement connectivity | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 2 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-06 | Installation of 8 Solar High Mast Lights | Installation of eight solar-powered high mast lights to improve safety, visibility and public security. | All wards (8 Solar High Mast Lights per Ward) | Poor lighting; crime vulnerability; unsafe pedestrian movement | Improve public safety and night-time usability of public spaces | Install lighting at community nodes and transport interfaces | Infrastructure development | Local communities | 1 year | [10 empty] | 7187552.23 | 2000000 | MIG | Planned | 2 | Theft of solar components, or battery failure may reduce functionality and shorten the lifespan of the lighting units. | Install tamper-proof fittings and secure battery enclosures, position lights in visible community nodes, and implement routine maintenance with community-based monitoring. | None | N/A
ID-07 | Estingini Access Road | Upgrade of Estingini Access Road to improve internal settlement accessibility and all-weather access | Ward 1 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen internal settlement connectivity | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 2 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-08 | Mantungwini Access Road and Bridge | Upgrade of Mantungwini Access Road and associated bridge structure to improve all-weather access and safe crossing. | Ward 7 | Seasonal inaccessibility due to flooding and poor surface condition, affecting scholar transport, emergency services and agricultural mobility | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-09 | Mphayeni Access Road | Upgrade of Mphayeni Access Road structure to improve all-weather access and safe crossing. | Ward 2 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 3582780.01 | 1000000 | DoT/ MIG | Registration | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-10 | Ophokweni Access Road | Upgrade of Mphayeni Access Road structure to improve all-weather access and safe crossing. | Ward 2 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-11 | Sgubudwini Access Road | Upgrade of Mphayeni Access Road structure to improve all-weather access and safe crossing. | Ward 2 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-12 | Nqgulunga Access Road with pedestrian bridge | Upgrade of Nqgulunga Access Road and associated bridge structure to improve all-weather access and safe crossing. | Ward 3 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-13 | Mantungwini Access Road and Bridge | Upgrade of Mantungwini Access Road and associated bridge structure to improve all-weather access and safe crossing. | Ward 7 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 4 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-14 | Nobhala Access Road Phase 2 | Upgrade of Nobhala Access Road to improve all-weather access and safe crossing. | Ward 3 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-15 | Gobhozini Access Road | Upgrade of Gobhozini Access Road to improve all-weather access and safe crossing. | Ward 4 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-16 | Gwala Access Road | Upgrade of Gwala Access Road to improve all-weather access and safe crossing. | Ward 4 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-17 | Qeleni Access Road | Upgrade of Qeleni Access Road to improve all-weather access and safe crossing. | Ward 5 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 4207806.89 | 1000000 | DoT/ MIG | Tender | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-18 | Ntweka Access Road Phase 2 (Nene) | Phase 2 upgrade of Ntweka Access Road to improve all-weather access and safe crossing. | Ward 5 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 6630583.45 | 1000000 | DoT/ MIG | Tender | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-19 | Kay Ngcongo Access Road | Upgrade of Kay Ngcongo Access Road to improve all-weather access and safe crossing. | Ward 6 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-20 | Kwaluzizi Access Road | Upgrade of Kwaluzizi Access Road to improve all-weather access and safe crossing. | Ward 6 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-21 | Mdakeni Access Road | Upgrade of Mdakeni Access Road to improve all-weather access and safe crossing. | Ward 6 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-22 | Egqumeni Access Road | Upgrade of Egqumeni Access Road to improve all-weather access and safe crossing. | Ward 6 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-23 | Khebhesi Pedestrian Bridge / Khebhesi Access Road with bridge | Upgrade of Khebhesi Access Road and associated bridge structure to improve all-weather access and safe crossing. | Ward 6 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-24 | Ndaya Access Road | Upgrade of Ndaya Access Road to improve all-weather access and safe crossing. | Ward 7 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-25 | Mkhangoma Access Road | Upgrade of Mkhangoma Access Road to improve all-weather access and safe crossing. | Ward 7 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
ID-26 | Mboyi Bridge | Construction or upgrading of Mboyi Bridge to provide safe, reliable river crossing and improve rural accessibility | Ward 3 | Seasonal flooding restricts movement, isolating households and limiting emergency access, school transport and agricultural mobility | Improve resilient rural connectivity and reduce vulnerability of isolated settlements | Upgrade critical river crossings along strategic rural access routes supporting service delivery and economic participation | Infrastructure development | Local communities | 3 years | [10 empty] | 5000000 | 1000000 | DoT/ MIG | Planned | 3 | Environmental approval delays and inaccurate floodline modelling | Initiate hydrological and environmental studies early and design above calculated flood return periods | Environmental screening/EIA | 2026
ID-27 | Matigulu Access Road | Construction of Matigulu Access Road to improve all-weather access and safe crossing | Ward 7 | Poor access during rain; unsafe conditions for scholars and emergency vehicles. | Strengthen rural connectivity and reduce isolation of peripheral settlements | Upgrade priority internal access roads serving high-density rural settlements | Infrastructure development | Local communities | 3 years | [10 empty] | 5975876.91 | 1000000 | MIG | Construction 61-80% | 3 | Flood damage; under-designed drainage. | Proper culvert sizing | None | N/A
SF-03 | Mkhambathini Library | Construction of a public library facility to expand access to learning resources, digital services and community study space. | Camperdown | Limited access to learning resources and safe study spaces; digital divide | Strengthen human capital development and community knowledge services | Concentrate higher-order social facilities in the primary node for maximum access and viability. | Social facilities development | Local communities | 3 years | [10 empty] | 15000000 | 1800000 | Operational funding after build; staffing | Planned | 2 | Operational funding after build; staffing | Secure operational budget; partnership with provincial library services | SPLUMA, building plan approvals | 2026
SF-04 | Mkhambathini Art Centre | Development of an arts and culture centre to support creative enterprise, community programmes and tourism-linked cultural activity. | Camperdown/ Maqongqo | Limited formal support space for arts/crafts and cultural economy | Support creative economy and local identity | Cluster cultural facilities to strengthen node-based social and tourism assets | Social facilities development | Local communities | 3 years | [10 empty] | 10000000 | 1000000 | EDTEA/ private sponsorships | Planned | 2 | Low utilisation if programming weak; operating cost burden. | Operator model and programming plan before construction; partnerships with EDTEA. | SPLUMA, building plan approvals | 2026
SF-05 | KwaNyavu Community Library | Construction of a community library to improve rural access to learning resources and basic ICT services. | KwaNyavu | Rural service access gap; limited study spaces; digital exclusion | Improve rural access to knowledge and educational resources | Provide lower-order community facilities within rural service clusters to reduce travel burden to Camperdown | Social facilities development | Local communities | 3 years | [10 empty] | 10000000 | 1000000 | EDTEA/ private sponsorships | Planned | 2 | Low utilisation if programming weak; operating cost burden. | Operator model and programming plan before construction; partnerships with EDTEA. | SPLUMA, building plan approvals | 2026
SF-06 | KwaNyavu Indoor Sport Centre | Development of an indoor multi-purpose sport centre to strengthen youth recreation, community sports programming and social cohesion | KwaNyavu / Banqobile area | Limited formal sport facilities; youth vulnerability; lack of structured recreation | Strengthen social infrastructure and youth development in rural settlements | Target rural clusters with high youth populations; integrate with school and community programming | Social facilities development | Local communities | 3 years | [10 empty] | 3000000 | 500000 | Mkhambathini/ SRSA | Planned | 2 | Operating costs; vandalism/security | Management model (community + municipal); security planning; partnership with schools | Land permission from TC | 2026
SF-07 | Estingini Sports Field | Development of the Estingini Sports Field to provide structured recreational space and improve youth sport participation. | Ward 1 | Limited formal sport infrastructure; youth vulnerability; informal use of unsafe open space | Improve equitable distribution of community facilities across rural wards | Strengthen rural service clusters through provision of basic community infrastructure under MIG | Social facilities development | Local communities | 3 years | [10 empty] | 18746798.65 | 5000000 | MIG | Planned | 2 | Vandalism; insufficient maintenance budget | Community-based facility management committee; phased facility improvements | Land permission from TC | 2026
SF-08 | White City Crèche | Construction of a formal Early Childhood Development (ECD) facility to improve early learning access and safe childcare. | Ward 1 | Lack of compliant early childhood facilities; informal childcare environments. | Strengthen social infrastructure and early childhood development outcome | Provide basic community facilities within walkable rural clusters | Social facilities development | Local communities | 3 years | [10 empty] | 3000000 | 500000 | MIG | Planned | 2 | Operational funding gap post-construction | Secure DSD registration and operational subsidy before construction | Building plan approval; ECD registration compliance | 2026
SF-09 | Bus / Taxi Shelters | Construction of formalised bus and taxi shelters to improve commuter safety and dignity. Concrete platform, covered shelter structure, seating, signage and drainage around platform | All Wards | Informal roadside waiting areas; exposure to weather; unsafe boarding conditions | Improve public transport user experience and road safety | Formalise transport stops along primary access roads and settlement spines | Social facilities development | Local communities | 1 year | [10 empty] | 1500000 | 350000 | MIG | Planned | 2 | Poor siting or lack of drainage may result in underutilisation, structural damage, or unsafe pedestrian conditions. | Conduct proper site assessments aligned to commuter movement patterns and provide adequate drainage and durable materials to ensure long-term usability and safety | None | N/A
SF-10 | Johnson Mkhize Crèche (Gulube) | Construction of a formal Early Childhood Development facility | Ward 7 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | DoE/ MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-11 | Mpangisa Creche | Construction of a formal Early Childhood Development facility | Ward 6 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | DoE/ MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-12 | Ngilandi Creche | Construction of a formal Early Childhood Development facility | Ward 5 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | DoE/ MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-13 | Osuthu Creche | Construction of a formal Early Childhood Development facility | Ward 4 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | DoE/ MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-14 | Cosmoore Crèche | Construction of a formal Early Childhood Development facility | Ward 3 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | DoE/ MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-15 | Nonzila Creche | Construction of a formal Early Childhood Development facility | Ward 2 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 5899950 | 1000000 | MIG | Construction 41-60% | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | None | N/A
SF-16 | Camperdown Crèche | Construction of a formal Early Childhood Development facility | Ward 3 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-17 | Dithi Mdluli Creche | Construction of a formal Early Childhood Development facility | Ward 2 | Lack of compliant ECD infrastructure in rural cluster | Improve early childhood education access and safe childcare facilities | Locate social facilities within walking distance of dense rural settlements | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | DoE/ MIG | Planned | 2 | Post-construction operational funding gap | Secure DSD registration and operational subsidy prior to completion | Building plan approval; ECD registration compliance | 2026
SF-18 | Mgwenya Sports Field with Grandstands | Development and formalisation of Mgwenya sports field including spectator seating | Ward 7 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-19 | Upgrade of Makholweni Sports Field with Grandstand | Upgrade and formalisation of Makholweni sports field including spectator seating | Ward 6 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-20 | KwaDwengu Sports Field with Grandstands | Development and formalisation of KwaDwengu sports field including spectator seating | Ward 6 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-21 | Upgrade of Ophokweni No.8 Sports Field with Grandstands | Upgrade and formalisation of Ophokweni No.8 sports field including spectator seating | Ward 2 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-22 | Construction of Nkanyezi Sports Field with Grandstands | Upgrade and formalisation of Nkanyezi sports field including spectator seating | Ward 3 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 10000000 | 2000000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-23 | Eston Sports Field with Grandstand | Upgrade and formalisation of Eston sports field including spectator seating | Ward 4 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-24 | Gulube Sports field | Development and formalisation of Gulube sports field | Ward 7 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-25 | Tala Valley Sports field | Development and formalisation of Gulube sports field | Ward 4 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 14889360.85 | 2000000 | MIG | Construction 81-99% | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-26 | Lombe Sports field | Development and formalisation of Lombe sports field including spectator seating | Ward 5 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-27 | Banqobile Sports Field Phase 2 | Phase 2 development and formalisation of Banqobile sports field including spectator seating | Ward 5 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 4000000 | 800000 | MIG | Planned | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-28 | Qalakahle Sports Field | Development and formalisation of Qalakahle sports field including spectator seating | Ward 2 | Limited structured recreation facilities and youth engagement platforms | Strengthen social cohesion and youth participation | Develop sport infrastructure within rural community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 14811960.47 | 1000000 | MIG | Tender | 2 | Underutilisation without formal programming | Establish community sports committee and event calendar | None | N/A
SF-29 | Mgwenya Community Hall | Construction of multipurpose community hall | Ward 7 | Lack of formal gathering and service-delivery venue | Strengthen community governance and service access | Provide community halls within rural clusters to decentralise service delivery | Social facilities development | Local communities | 3 years | [10 empty] | 8000000 | 1000000 | MIG | Planned | 2 | Underutilisation of the facility and vandalism due to weak management structures and limited programmed activities. | Establish a formal community management committee, supported by basic security measures (controlled access, perimeter fencing and lighting) | SPLUMA, building plan approvals | 2026
SF-30 | Ntweka Community Hall | Construction of multipurpose community hall | Ward 5 | Lack of formal gathering and service-delivery venue | Strengthen community governance and service access | Provide community halls within rural clusters to decentralise service delivery | Social facilities development | Local communities | 3 years | [10 empty] | 8000000 | 1000000 | MIG | Planned | 2 | Underutilisation of the facility and vandalism due to weak management structures and limited programmed activities. | Establish a formal community management committee, supported by basic security measures (controlled access, perimeter fencing and lighting) | SPLUMA, building plan approvals | 2026
SF-31 | Cosmoore Community Hall | Construction of multipurpose community hall | Ward 3 | Lack of formal gathering and service-delivery venue | Strengthen community governance and service access | Provide community halls within rural clusters to decentralise service delivery | Social facilities development | Local communities | 3 years | [10 empty] | 8000000 | 1000000 | MIG | Planned | 2 | Underutilisation of the facility and vandalism due to weak management structures and limited programmed activities. | Establish a formal community management committee, supported by basic security measures (controlled access, perimeter fencing and lighting) | SPLUMA, building plan approvals | 2026
SF-32 | Imboyi Community Hall | Construction of multipurpose community hall | Ward 4 | Lack of formal gathering and service-delivery venue | Strengthen community governance and service access | Provide community halls within rural clusters to decentralise service delivery | Social facilities development | Local communities | 3 years | [10 empty] | 7860771.74 | 2000000 | MIG | Construction 81-99% | 2 | Underutilisation of the facility and vandalism due to weak management structures and limited programmed activities. | Establish a formal community management committee, supported by basic security measures (controlled access, perimeter fencing and lighting) | None | N/A
SF-33 | Nonzila Community Hall | Construction of multipurpose community hall | Ward 2 | Lack of formal gathering and service-delivery venue | Strengthen community governance and service access | Provide community halls within rural clusters to decentralise service delivery | Social facilities development | Local communities | 3 years | [10 empty] | 8000000 | 1000000 | MIG | Planned | 2 | Underutilisation of the facility and vandalism due to weak management structures and limited programmed activities. | Establish a formal community management committee, supported by basic security measures (controlled access, perimeter fencing and lighting) | SPLUMA, building plan approvals | 2026
SF-34 | Outdoor Gym | Installation of outdoor fitness equipment in public open space. Fixed steel gym equipment, basic lighting and signage | Ward 7 | Limited structured recreational and wellness infrastructure. | Promote community health and active lifestyle | Integrate low-cost wellness infrastructure into community nodes | Social facilities development | Local communities | 3 years | [10 empty] | 1000000 | 200000 | MIG | Planned | 2 | Equipment vandalism. | Secure installation and community stewardship | SDP appproval | 2026
SF-35 | Eston Taxi Rank | Development of Eston Taxi Rank integrated with formalised market stalls to support public transport operations and local informal trade | Ward 4 | Informal and poorly structured taxi operations and trading activities leading to congestion, safety risks and limited economic formalisation | Strengthen Eston as a functional secondary service and economic node | Formalise transport interfaces and integrate informal trade infrastructure to stimulate local economic activity | Social facilities development | Local communities | 3 years | [10 empty] | 12000000 | 1200000 | MIG | Planned | 2 | Conflict between taxi associations and traders or underutilisation | Conduct structured stakeholder engagement and confirm site alignment with existing commuter movement patterns before final design | Rezoning or consent use (if required); Site Development Plan approval; building plan approval. | 2026
PLN-01 | Development of New Town (Industrial, Commercial & Residential) | 50–100 ha phased mixed-use precinct; Industrial logistics platforms; CBD expansion block; 800–1500 residential units (mixed typology); Internal road grid & bulk services | Adjacent to Camperdown CBD, N3-adjacent land parcels | Need for diversified economic development | Establish Camperdown as a secondary logistics-industrial hub within uMgungundlovu. | Corridor intensification and urban edge consolidation. | Catalytic Mixed-Use Growth Precinct | Investors, local SMMEs, future households, EPWP participants | 10 year phased rollout | [10 empty] | R400 million (phased) | 60000000 | PPP, Private investment, MIG | Pre-feasibility / Land negotiation | 4 | Land acquisition delays, Market absorption risk, Bulk capacity dependency (WWTW) | Phased release; Pre-commitment from logistics firms; Link to WWTW sequencing | Township establishment; Rezoning; EIA; Bulk service agreements | 2027
INF-29 | N3 Corridor Upgrade | Upgrade and expansion of the N3 corridor section traversing Mkhambathini to improve freight. mobility, safety and regional accessibility. Road widening and resurfacing; Interchange improvements; Stormwater upgrades | N3 Corridor | Constrained freight capacity; under-leveraged corridor investment potential | Position Mkhambathini as a strategic logistics-linked rural municipality along the N3 growth corridor. | Leverage national transport infrastructure to unlock industrial, agro-processing and mixed-use investment along corridor influence areas. | National transport infrastructure upgrade | Freight operators; local industries; agro-processors; commuters; investors. | 5 years (multi-phase construction) | [10 empty] | TBD | TBD | SANRAL (External) | Ongoing / External-led | 4 | Construction delays; limited municipal alignment; access control constraints. | Integrated corridor planning; early land-use alignment; intergovernmental coordination. | Access approvals | Ongoing
INF-30 | Bulk Wastewater Treatment Works Upgrade | Expansion and upgrading of bulk wastewater treatment capacity to support housing, industrial and commercial development. Increased treatment capacity; Reticulation upgrades; Effluent quality compliance systems; Bulk pipeline connections | Camperdown | Insufficient wastewater capacity; development constraints; environmental compliance pressures. | Enable structured urban expansion and industrial growth within designated nodes. | Align bulk services investment with nodal growth areas and corridor-linked development. | Bulk infrastructure development | Residents; developers; industries; commercial investors. | 10+ years: Current IDP: Feasibility and design (current IDP term); Infrastructure implementation (5 years); Capacity scaling with growth (10+ years) | [10 empty] | TBD | TBD | External (UMDM; Umgeni Water) | Planned / External | 4 | Funding gaps; environmental approvals; capacity mismatch. | Phased capacity expansion; alignment with SDF growth projections. | Environmental Authorisation; Water Use Licence; servitude registration. | 2027
LED-01 | Mkhambathini Agri-Park (Farmer Support Unit) | Establishment of a Farmer Support Unit and agricultural produce aggregation facility. Storage warehouses. Training facility, market trading platform, equipment and input support services | Eston | Fragmented emerging farmer support; lack of aggregation facilities; limited market penetration. | Strengthen agricultural value chains and support emerging farmers. | Develop decentralised agri-support infrastructure linked to production zones and corridor markets. | LED/ Agriculture development | Emerging farmers; cooperatives; agri-entrepreneurs. | 8 years (multi-phase construction) | [10 empty] | TBD | TBD | UMEDA; RASET; External grant | Grant application stage | 3 | Operational sustainability; grant dependency. | Public-private management model; capacity building programmes. | Land allocation; rezoning (if required); SDP approval. | 2027
LED-02 | Red Meat Processing Hub | Development of a livestock processing and red meat hub to strengthen food systems and livestock quality. Proposed Specifications, abattoir facility, cold storage, veterinary inspection area | Eston | Limited local processing capacity; value chain leakage; food security vulnerability. | Improve livestock beneficiation and local food security. | Cluster meat processing near livestock production zones; integrate into regional markets. | LED/ Agriculture development | Livestock farmers; cooperatives; local retailers; households. | 4–6 years | [10 empty] | TBD | TBD | DARD (External) | Proposed | 3 | Compliance requirements; high capital cost | Phased facility scale; regulatory early engagement | Environmental Authorisation; Possible zoning | 2027