## Sheet1
MKHAMBATHINI LOCAL MUNICIPALITY
Department : Technical Services
KPA: Basic Service Delivery
No | Project Name | Delivery Objective | Start Date | End Date | July | August | September | October | Novenber | December | January | February | March | April | May | June
1 | Ngoloshini Sportfield | Constraction of Sportfield | 2010-07-01 | 2011-02-01 | July: 700000; September: 700000; December: 700000
2 | Muzi Gumede Hall | Constraction of Community Hall | 2010-08-01 | 2010-12-01 | August: 333000; October: 333000; Novenber: 334000
3 | Nungwane Hall | Constraction of Community Hall | 2010-08-01 | 2010-12-01 | August: 333000; September: 333000; December: 334000
4 | Scot Street | Contraction of road | 2010-07-01 | 2010-09-01 | July: 300000
5 | Mahlabathini Sportfield | upgrade of Sportfield | 2010-07-01 | 2010-11-01 | July: 500000; October: 500000
6 | Mpangisa sportfield | Constraction of Sportfield | 2010-07-01 | 2010-02-01 | July: 400000; September: 400000; October: 200000
7 | Bebhuzi Sportfield | Constraction of Sportfield | 2010-07-01 | 2010-10-01 | August: 250000; October: 250000
8 | Gijima Creche | Buildimg of comm Creche | 2010-09-01 | 2011-01-01
9 | Gqaza Creche | Buildimg of comm Creche | 2010-10-01 | 2011-01-01 | October: 250000; December: 250000
10 | Ismont Creche | Buildimg of comm Creche | 2010-10-01 | 2011-01-01 | Novenber: 250000; January: 250000
11 | Sabelo Creche | Buildimg of comm Creche | 2010-10-01 | 2011-01-01 | Novenber: 250000; January: 250000
12 | Thokozani Creche | Buildimg of comm Creche | 2010-10-01 | 2011-01-01 | Novenber: 250000; January: 250000
|  | Total Cost Per Month |  |  | 1900000 | 916000 | 1433000 | 1533000 | 1084000 | 1284000 | 750000 | 0 | 0 | 0 | 0 | 0